## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: OFFICE OF TRANSFORMATION,CREATIVITY AND INNOVATION
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Personnel Management Board | OTCI/NP/NM/001/22 | 1490050 | Plan | MAY: 1490050
Actual
2 | Monthly meetings of Lagos State Technucal Committee on EODB (Logistics/Allowances) | OTCI/NP/NM/002/22 | 1,000,000.00 | Plan | APRIL: 250000; MAY: 250000; JUNE: 250000; JULY: 250000
Actual
3 | Compliance monititoring& Evaluation ,including periodic mystery shopper element | OTCI/NP/NM/003/22 | 500,000.00 | Plan | APRIL: 125000; MAY: 125000; JUNE: 125000; JULY: 125000
Actual
4 | LASG's Participation at the DAWN Commission | OTCI/NP/NM/004/22 | 2,810,000.00 | Plan |  | 281.077.00 | 281.077.00 | 281.077.00 | 281.077.00 | 281.077.00 | 281.077.00 | 281.077.00 | 281.077.00 | 281.077.00 | 281.077.00
Actual
5 | Servicing of Monthly Committeee meeting on Service Charter and Reforms Initiatives) | OTCI/NP/NM/005/22 | 3200000 | Plan |  |  | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000
Actual
6 | Servicing of Management and Quarterly meeting of Senior &Junior Staff and Ad-hoc Meeting | OTCI/NP/NM/006/22 | 1,650,000.00 | Plan | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500 | 137500
Actual
7 | Managing reforms initiative by MDAs Service Wide (HR Implementation) | OTCI/NP/NM/007/22 | 8,463000 | Plan | MARCH: 2115750; MAY: 2115750; JULY: 2115750; OCTOBER: 2115750
Actual
8 | Implemement and Drive Ease of Doing Business National/Subnational mandate of PEBEC in Lagos. | OTCI/NP/NM/009/22 | 1,000,000.00 | Plan | MAY: 250000; JUNE: 250000; JULY: 250000; AUGUST: 250000
Actual
9 | Implemement EODB at Sub-National level working within the South-West. | OTCI/NP/NM/010/22 | 1,000,000.00 | Plan | MAY: 250000; JUNE: 250000; JULY: 250000; AUGUST: 250000
Actual
10 | Miscellaneous Expenses(Unforseen day to day and monthly Expenses | OTCI/NP/NM/11/22 | 4,200,000.00 | Plan | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
Actual
12 | Specialized Cleaning of Toilets, Lobby,Offices and Front Offices | OTCI/NP/NM/12/22 | 1500000 | Plan | SEPTEMBER: 350000; OCTOBER: 350000; NOVEMBER: 350000; DECEMBER: 350000
Actual
13 | Transport Allowances for Dispatch. | OTCI/NP/NM/12/22 | 2400000 | Plan | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
Actual
| List of PPC Committee. | DEPARTMENT | SIGNATURE
1 | Mr Toba Otusanya | Director General
2 | Mr. Shobajo. N.A | Dir. A&HR
3 | Mrs Anjous-Ademuyiwa. | DD,C&I
4 | Mr. Abdul Waliu. A | DD, Accounts.
5 | Mr. Otunuyi. O. | DD, Reforms
6 | Mr. Odebamowo | DD, MSD
7 | Mrs Seriki. G.T. | AD,Progms
8 | Mrs Meghoma T. | AD,Planning.
9 | Mrs Omolase. Y. | HOU-Public Affairs
10 | Mrs Otunuga. V. | HOU-ICT
11 | Okoya-Adelanwa, I.S | HOU-Procurement
12 |  | HOU-Audit

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: OFFICE OF TRANSFORMATION CREATIVITY AND INNOVATION
YEAR: | YR2022
S/N | Description of Training/Workshop/ Conference | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Allowances for staff for workshop and Training |  | 20 |  | Plan | Lagos |  |  |  | 921129
Actual
2 | Annual Subscription and Mandatory Continuing Professional Education (MCPDE) Accounts. | Professional Orientation and Career Progression | 5 | 4 Days | Plan | Abuja | 300000 | 475000 | 375000 | 1150000
Actual
3 | CIPM,NIM,Other professional body,NIPR&NITAD) etc. | Professional Orientation and Career Progression | 35 | 4Days | Plan | Abeokuta | 1593000 | 306000 | 5101000 | 7000000
Actual
4 | COWLSO | supporting the Lagos State Government Developmental effort from the Women’s perspective. | 14 | 3 Days | Plan | Lagos | 1080000 | 117560 |  | 1197560
Actual
5 | Annaul Account Retreat | Professional Orientation and Career Progression | 5 | 4 Days | Plan |  |  |  |  | 1350000
Actual
6 | Capacity Building for C&I Ambassadors Service wide per Quarter |  |  | 5 Days | Plan |  |  |  |  | 3000000
Actual
7 | C&I Awareness Sensitization Serve Wide per Quarter |  |  |  | Plan |  |  |  |  | 7700000
Actual
8 | Capacity Building for Lagos State Citizens Gate Resolvers and Supervisors (CRM) |  |  |  | Plan |  |  |  |  | 1500000
Actual
9 | Annual OTCI Retreat | Review the benchmark for the year,Set Target for coming year and Plan strategies in achieving the core Mandate of the Office with THEMES | 5 | 4Days | Plan |  |  |  |  | 7501000
Actual
10 | Knowldege Sharing Sessions(OTCI Staff) |  | 52 |  | Plan |  |  |  |  | 5000000
Actual
Plan
Plan
| TOTAL |  |  |  | Actual |  |  |  |  | 36319689

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
BUDGET YEAR: YR2022
Contract Description |  | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Sentisitization/Awareness of Service Charter Week |  | OTCI/S-NC/NS/001/22 |  |  | 8000300 | <10M | NS | Plan | POST | POST | NA | NA | NA | NA | NA | NA | NA | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
Engagement of facilitatotors on Citizens gate Resolvers |  | OTCI/S-NC/NS/002/22 |  |  | 1000000 | <10M | NS | Plan | POST | POST | NA | NA | NA | NA | NA | NA | NA | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
Structure and Re-structuring of MDAs Consultancy Assignment | Structure and Re-structuring of MDAs Consultancy Assignment | OTCI/S-NC/NS/003/22 |  |  | 4000000 | <10M | NS | Plan | POST | POST | NA | NA | NA | NA | NA | N A | NA | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
SPADEV Compliance Monitoring | SPADEV Compliance Monitoring | OTCI/S-NC/NS/004/22 |  |  | 2825000 | <10M | NS | Plan | POST | POST | NA | NA | NA | NA | NA | NA | NA | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
Developing Corporate Planning processes in MDAs | Developing Corporate Planning processes in 2 Nos MDAs | OTCI/S-NC/NS/005/22 |  |  | 2500000 | <10M | NS | Plan | POST | POST | NA | NA | NA | NA | NA | NA | NA | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
Implementation and Monitoring Process on Corporate Planning for MDAs in Lagos State Public Service | Implementation and Monitoring Process on Corporate Planning for MDAs in Lagos State Public Service | OTCI/S-NC/NS/006/22 |  |  | 2500000 | <10M | NS | Plan | POST | POST | NA | NA | NA | NA | NA | NA | NA | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
Growth Mindset Phase 11 covering MDAs, LGAs,and General Hospitals |  | OTCI/S-NC/NS/007/22 |  |  | 2,500,00.000 | <10M | NS | Plan | POST | POST | NA | NA | NA | NA | NA | NA | NA | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
Stakeholders Engagement on Ease of Doing Business |  | OTCI/S-NC/NS/008/22 |  |  | 72307670 | <100M | NS | Plan | POST | POST | 2022-02-10 | 2022-02-14 | 2022-02-21 | 2022-02-06 | 2022-02-13 | 2022-03-20 | 2022-03-27 | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
Smart City Innovation Competition (Talent Hunt) |  | OTCI/S-NC/NS/009/22 |  |  | 9000000 | <10M | NS | Plan | POST | POST | 2022-02-10 | 2022-02-14 | 2022-02-21 | 2022-02-06 | 2022-02-13 | 2022-03-20 | 2022-03-27 | Plan | 2022-04-06 | 2022-04-08 |  | 2022-05-06 | 2022-05-13 | 2022-05-27 | 2022-05-27
[8 empty] | Actual | [9 empty] | Actual
| List of PPC Committee. | DEPARTMENT | SIGNATURE
1 | Mr Toba Otusanya | Director General
2 | Mr. Shobajo. N.A | Dir. A&HR
3 | Mrs Anjous-Ademuyiwa. | DD,C&I
4 | Mr. Abdul Waliu. A | DD, Accounts.
5 | Mr. Otunuyi. O. | DD, Reforms
6 | Mr. Rufai Olalekan | DD, BOS
7 | Mr. Odebamowo O. | DD,MSD
7 | Mrs Seriki. G.T. | AD,Progms
8 | Mrs Meghoma T. | AD,Planning.
9 | Mrs Omolase. Y. | HOU-Public Affairs
10 | Mrs Otunuga. V. | HOU-ICT
12 | Okoya-Adelanwa, I.S | HOU-Procurement
13 | Mrs Akinpelumi | HOU-Audit

## Sheet1
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: OFFICE OF TRANSFORMATION,CREATIVITY AND INNOVATION
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Allowances for staff for workshop and Training | OTCI/S-WTC/SSS/001/22 |  | 11 |  | Plan | Lagos |  |  |  | 921129
Actual
2 | Annual Subscription and Mandatory Continuing Professional Education (MCPDE) | OTCI/S-WTC/SSS/002/22 | Professional Orientation and Career Progression | 5 | 4 days | Plan | Abuja |  |  |  | 650000
Actual
3 | CIPM,NIM,Other professional body (Nigerian Statistical Association,ICAN,ANAN,CIPMNS,CPN,NIPR&NITAD) etc. | OTCI/S-WTC/SSS/003/22 | Professional Orientation and Career Progression | 10 | 4Days | Plan | Abuja |  |  |  | 2000000
Actual
4 | COWLSO | OTCI/S-WTC/SSS/004/22 | Professional Orientation and Career Progression | 7 | 3 Days | Plan |  |  |  |  | 197560
Actual
5 | Annaul Account Conference | OTCI/S-WTC/SSS/005/22 | Develop Officers ability and this will impact positively while discharging there duties. | 5 | 4 Days | Plan |  |  |  |  | 850000
Actual
6 | Capacity Building for C&I Ambassadors Service wide per Quarter | OTCI/S-WTC/SSS/006/22 | Support the Lagos State Government Developmental effort from the women's perspective |  | 5 Days | Plan |  |  |  |  | 2000000
Actual
7 | C&I Awareness Sensitization Serve Wide per Quarter | OTCI/S-WTC/SSS/007/22 | Professional Orientation and Career Progression |  |  | Plan |  |  |  |  | 6000000
Actual
8 | Annual Retreat | OTCI/S-WTC/SSS/009/22 | Review the benchmark for the year,set target for coming year and Plan strategies in achieving the core mandate of the Office with THEMES. | 66 | 4Days | Plan |  |  |  |  | 850000
Actual
9 | Capacity Building for Lagos State Citizens Gate Resolvers and Supervisors (CRM) | OTCI/S-WTC/SSS/010/22 |  |  |  | Plan |  |  |  |  | 1020000
Actual
| TOTAL | [9 empty] | 14488689

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: OFFICE OF TRANSFRMATION,CREATIVITY AND INNOVATION
BUDGET YEAR: YR2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
- |  |  |  |  | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Smart City Innovation Competition(Talent Hunt) | OTCI/S-C/SSS/001/22 | SSS |  | 9000000 | POST | Plan | 03-02-2022 | 10-02-2022 | 17-02-2022 | 09-03-2022 | 16-03-2022 | 23-03-2022 | 13-04-2022 | 20-04-2022 | 27-04-2022 | 04-05-2022 | 11-05-2022 | 18-05-2022 | 25-05-2022 | 27-05-2022 |  | 03-06-2022 | 17-06-2022 | 01-07-2022 | 08-07-2022 | 15-07-2022
Actual
| List of PPC Committee. | DEPARTMENT | SIGNATURE
1 | Mr Toba Otusanya | Director General
2 | Mr. Shobajo. N.A | Dir. A&HR
3 | Mrs.Anjous-Ademuyiwa T. | DD,C&I
4 | Mr. Otunuyi. O. | DD, Reforms
5 | Mr. Abdul W. A | DD,Accounts
6 | Mr. Rufai Olalekan | DD, BOS
7 | Mr. Odebamowo | DD,MSD
9 | Mrs Grace seriki | AD,Progms
10 | Mrs Meghoma. T. | HOU-Planning
11 | Mrs Otunuga. V. | HOU-ICT
12 | Okoya-Adelanwa, I.S | HOU-Procurement
13 |  | HOU-Audit

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: OFFICE OF TRANSFORMATION,CREATIVITY AND INNOVATION
BUDGET YEAR:YR 2022
S/N | CONTRACT IDENTIFICATION |  |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number |  | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[13 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Management Information System(MIS) ,Replacemet of desktop/laptops computer Aceessories |  | OTCI/G/NS/001/22 |  |  | LS | 2500000 | <10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-03-27 | 2022-03-30 |  | 2022-04-01 | 2022-04-06 | 2022-04-13 | 2022-04-27 | 2022-04-28
Actual
2 | OTCI Service Delivery Unit(Procurement of branded T.shirts and other items) |  | OTCI/G/NS/002/22 |  |  | LS | 500000 | <10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-04-01 | 2022-04-03 |  | 2022-04-06 | 2022-04-10 | 2022-04-13 | 2022-04-16 | 2022-04-16
Actual
3 | Procurement of Uniform, Toiletries and Protective Outfit |  | OTCI/G/NS/003/22 |  |  | LS | 1915000 | <10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-05-27 | 2022-05-29 |  | 2022-06-01 | 2022-06-05 | 2022-06-19 | 2022-07-02 | 2022-06-02
Actual
4 | Procurement of Cleaning Materials |  | OTCI/G/NS/004/22 |  |  | 4 | 715000 | <10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
5 | Cordinator/Programmes Unit Expenses (Binding &Printing of reports) |  | OTCI/G/NS/005/22 |  |  | 4 | 1000000 | <10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
6 | Procurement of Generator Set.30kva. |  | OTCI/G/NS/006/22 |  |  | 1 | 8000000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
7 | Procurement of Consumables,Stationeries and Working tools for 5(Units) |  | OTCI/G/NS/007/22 |  |  | 4 | 5000000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
8 | Procurement of Office Cabinets, Window blinds,Executive tables and Chairs. |  | OTCI/G/NS/008/22 |  |  | 25 | 4000000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
9 | Procurement of Working Materials for Planning Unit |  | OTCI/G/NS/009/22 |  |  | 4 | 2000000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
10 | Procurement of Stationeries Items for departments/Units |  | OTCI/G/NS/010/22 |  |  |  | 3000000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
11 | Maintenance of Office Building (Such as replacement of damaged keys,plugs,sockets doors et.c) |  | OTCI/G/NS/011/22 |  |  | LS | 1800000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
12 | General Utility (Recharge cards,Monthly subscriptions for cables, dstv,etc) |  | OTCI/G/NS/012/22 |  |  | LS | 1800000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
13 | Motor vehicle Repair( Purchase of Tyres and Servocing of official Vehicles) |  | OTCI/G/NS/013/22 |  |  | LS | 2400000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
14 | General Utility (Recharge cards,Monthly subscriptions for cables, dstv,etc) |  | OTCI/G/NS/014/22 |  |  | LS | 1800000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
15 | Purchase of Fuel for 6nos of Official Vehicles |  | OTCI/G/NS/015/22 |  |  | LS | 2400000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
16 | Staff Welfare(Purchase of Gifts items, Data for Management and Junior Staff) |  | OTCI/G/NS/016/22 |  |  | LS | 7000000 | 10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | 2022-06-25 | 2022-06-29 |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-20
Actual
|  | List of PPC Committee. | DEPARTMENT | SIGNATURE
| 1 | Mr Toba Otusanya | Director General
| 2 | Mr. Shobajo. N.A | Dir. A&HR
| 3 | Mrs Anjous-Ademuyiwa T. | D, C&I
| 3 | Mr. Abdul Waliu. A | DD,Accounts
| 4 | Mr. Otunuyi Adejimi | DD, Reforms
| 5 | Mr. Odebamowo. O | DD, MSD
| 6 | Mr.Rufai Olalekan | DD, BOS
| 7 | Mrs Seriki. T | AD,Progms
| 8 | Mrs Meghoma T. | HOU-Planning
| 8 | Mrs Otunuga. V. | HOU-ICT
| 10 | Okoya-Adelanwa, I.S | HOU-Procurement
| 11 | Mrs. Akinpelumi | HOU-Audit

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF TRANSFORMATION, CREATIVITY AND INNOVATION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Renovation of DG's Office and Creativity and Innovation Dept. | OTCI/W/NS/001/22 | 1 | 8000000 | 10M | NS | BOQ | POST | Plan | POST | 2022-05-06 | NA | NA | NA | NA | 2022-06-18 |  |  |  | 2022-07-01 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-27
Actual