## GOODS
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  |  | BASIC DATA | [5 empty] | Plan/Actual | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail. in Naira | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hours | 0 | 1 wk | 1-2wks | 2-4 wks | 4wk
1 | Procurement of Computer & systems | LSP/G/NCB/001/22 | 1 | various | 80,480,000.00 | <100M | NCB | POST | PRIOR | Plan | 18/02/22 | 04/03/22 | 18/03/22 | 29/04/22 | 13/05/22 | 27/05/22 | 25/06/22 | 25/06/22 |  | 01/07/22 | 15/07/22 | 12/08/22 | 09/09/22 | NA
Actual
2 | Procurement of Classroom Furniture & Fittings-for SOT | LSP/G/NS/002/22 | 1 | Various | 31,500,000.00 | <100M | NS | POST | PRIOR | Plan | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | 03/06/22 | 01/07/22 | 01/07/22 |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
3 | Procurement of Motor Vehicles & Buses | LSP/G/NCB/003/22 | 1 | Various | 192,220,000.00 | >100M | NCB | POST | PRIOR | Plan | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
4 | Procurement of Plant & Machinery for all Schools | LSP/G/NCB/004/22 | 1 | Various | 50,000,000.00 | <100M | NCB | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | NA
Actual
5 | Procurement of Security Equipment | LSP/G/NS/005/22 | 1 | Various | 10,000,000.00 | <100M | NS | POST | PRIOR | Plan | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 25/06/22 | 22/07/22 | 22/07/22 |  | 29/07/22 | 12/08/22 | 09/09/22 | 07/10/22 | NA
Actual
1 | Maintenance of Equipment & Machine -Procurement of 10hp submersible pump, workshop tools & equipment, gun powder for fire arms | LSP/G/NS/001/22 | 1 | Various | 4,600,000.00 | <10M | NS | POST | POST | Plan | 25/03/22 | 08/04/22 | 22/04/22 | 03/06/22 | 18/06/22 | NA | NA | NA |  | 05/08/22 | 19/08/22 | 16/09/22 | 14/10/22 | NA
Actual
2 | Procurement of Stationeries- Hardcover note book, A4 paper, Flat file, student file jacket, official envelop, black RZ ink, biros, staple pin, staple machine | LSP/G/NCB/002/22 | 1 | Various | 58,918,078.40 | <100M | NCB | POST | PRIOR | Plan | 18/02/22 | 04/03/22 | 18/03/22 | 29/04/22 | 13/05/22 | 27/05/22 | 25/06/22 | 25/06/22 |  | 01/07/22 | 15/07/22 | 12/08/22 | 09/09/22 | NA
Actual
3 | Procurement of Uniform & Protective Outfit-production of academic gown, laboratory uniform, watchman uniform and cardigan, safety boat, raincoat for security personnel | LSP/G/NS/003/22 | 1 | 150 | 2,895,000.00 | <10M | NS | POST | POST | Plan | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | NA | NA | NA |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
4 | Printing & Production Expenses - printing of seasonal publication (Calendar), EED Logbook, EED textbook, SIWES log book, Answer sheets, academic certificate | LSP/G/NCB/004/22 | 1 | Various | 137,513,818.00 | >100M | NCB | POST | PRIOR | Plan | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
5 | Procurement of Laboratory Reagent, Consumables & Teaching aid - vacination, medication & vet expenses, procurement of Seedding, livestock & fish feeds, teaching aid and consumables | LSP/G/NCB/005/22 | 1 | Various | 101,953,600.00 | >100M | NCB | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | NA
Actual
6 | Management Information System expenses- procurement of photocopy toner, laptop battery charger, APC Extension box, printers toner, Optical mouse, flash drive, Power pack, desktop harddrive, motherboard, power cable | LSP/G/NS/006/22 | 1 | Various | 42,950,700.00 | <100M | NS | POST | PRIOR | Plan | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 25/06/22 | 22/07/22 | 22/07/22 |  | 29/07/22 | 12/08/22 | 09/09/22 | 07/10/22 | NA
Actual
7 | Health Care & Medical Expenses- Procurement of Medical Lab reagent, (chemicals, x-ray films, gloves), procurement of medical drugs from manufacturer for dispensing to students on needs basis | LSP/G/NS/007/22 | 1 | Various | 23,600,000.00 | <100M | NS | POST | PRIOR | Plan | 25/03/22 | 08/04/22 | 22/04/22 | 03/06/22 | 18/06/22 | 01/07/22 | 29/07/22 | 29/07/22 |  | 05/08/22 | 19/08/22 | 16/09/22 | 14/10/22 | NA
Actual
13 | Accreditation-Procurement of Equipments for Agric & Bio- Environmental Engineering | LSP/G/NS/013/22 | 1 | Various | 25,717,600.00 | <100M | NS | POST | PRIOR | Plan | 18/02/22 | 04/03/22 | 18/03/22 | 29/04/22 | 13/05/22 | 27/05/22 | 25/06/22 | 25/06/22 |  | 01/07/22 | 15/07/22 | 12/08/22 | 09/09/22 | NA
Actual
14 | Accreditation-Procurement of Equipments for Chemical Engineering | LSP/G/NS/014/22 | 1 | Various | 18,990,032.00 | <100M | NS | POST | PRIOR | Plan | 18/02/22 | 04/03/22 | 18/03/22 | 29/04/22 | 13/05/22 | 27/05/22 | 25/06/22 | 25/06/22 |  | 01/07/22 | 15/07/22 | 12/08/22 | 09/09/22 | NA
Actual
15 | Accreditation-Procurement of Equipments for Civil Engineering | LSP/G/NS/015/22 | 1 | Various | 39,442,600.00 | <100M | NS | POST | PRIOR | Plan | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | 03/06/22 | 01/07/22 | 01/07/22 |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
16 | Accreditation-Procurement of Equipments for Electrical/Electronics Engineering | LSP/G/NS/016/22 | 1 | Various | 9,028,000.00 | <10M | NS | POST | PRIOR | Plan | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
17 | Accreditation-Procurement of Equipments for Mechanical Engineering | LSP/G/NCB/017/22 | 1 | Various | 50,185,920.00 | >100M | NCB | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | NA
Actual
18 | Accreditation-Procurement of Equipments for Mechatronic Engineering | LSP/G/NCB/018/22 | 1 | Various | 58,027,674.40 | >100M | NCB | POST | PRIOR | Plan | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 25/06/22 | 22/07/22 | 22/07/22 |  | 29/07/22 | 12/08/22 | 09/09/22 | 07/10/22 | NA
Actual
19 | Accreditation-Procurement of Equipment for Instrumentation Laboratory | LSP/G/NS/019/22 | 1 | Various | 26,817,893.60 | <100M | NS | POST | PRIOR | Plan | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
20 | Accreditation-Procurement of Equipments for Re-accreditation of HND Horticulture and Landscape Technology Programme (Laboratory items) | LSP/G/NS/020/22 | 1 | Various | 25,257,050.00 | <100M | NS | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | NA
Actual
8 | Cleaning & Landscaping expenses- Chemical for weed weakening such as forceup & tools for park and Garden | LSP/G/NS/008/22 | 1 | Various | 24,842,188.80 | <100M | NS | POST | POST | Plan | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | 03/06/22 | 01/07/22 | 01/07/22 |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
22 | Procurement of Library Books | LSP/G/NS/022/22 | 1 | Various | 50,000,000.00 | <100M | NS | POST | PRIOR | Plan | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
9 | Motor Vehicle Fuel Consumption-Fuel Grant for Principal officer, School/departmental officers car, Fuelling of Utility Buses and other Polytechnic event | LSP/G-F/NS/001/22 | 1 | Various | 96,836,892.80 | <100M | NS | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | NA
Actual
10 | Maintenance of office Building-replacement of bulb & door lock | LSP/G-F/NS/002/22 | 1 | Various | 2,380,000.00 | <10M | NS | POST | POST | Plan | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | NA | NA | NA |  | 29/07/22 | 12/08/22 | 09/09/22 | 07/10/22 | NA
Actual
11 | Motor Vehicle Repair & Maintenance - replacement of tyres and batteries | LSP/G-F/NS/003/22 | 1 | Various | 6,756,000.00 | <10M | NS | POST | POST | Plan | 25/03/22 | 08/04/22 | 22/04/22 | 03/06/22 | 18/06/22 | NA | NA | NA |  | 05/08/22 | 19/08/22 | 16/09/22 | 14/10/22 | NA
Actual
12 | Maintenance of Infrastructures (Laboratory & Lecture Room)- provision for electrical maintenance materials needs to central store, provision for Electrical, Plumbing fitting purchases, repairs and other sundry maintenance needs | LSP/G-F/NS/004/22 | 1 | Various | 6,760,000.00 | <10M | NS | POST | POST | Plan | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | NA | NA | NA |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
13 | Governing Council-- Provision for council Utility Bus Fuelling and Stationeries, council utility bus fueling | LSP/G-F/NS/005/22 | 1 | Various | 7,820,800.00 | <10M | NS | POST | POST | Plan | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | NA | NA | NA |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
14 | Fuelling & Maintenance of Generator expenses-Fueling of Generator | LSP/G-F/NCB/006/22 | 1 | 14 | 120,556,800.00 | >100M | NCB | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | NA
Actual
| TOTAL COST |  |  |  | 1306050648 |  |  |  |  | Plan

## WORKS
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  |  | BASIC DATA |  |  |  |  | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  |  |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | Budget Avail. in Naira | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qual |  |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governors Approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4wks | 48hrs | 0 | 1 wk | 1-2wks | 2-4 wks | 4wks
1 | Construction of School of Technology Complex at Ikorodu Campus (Block D)-- ON GOING | [7 empty] | Plan
|  | LSP/W/NCB/001/21 | 1 | 241,151,597.00 | >100M | NCB | BOQ | POST | Actual | PRIOR | [7 empty] | ON GOING
2 | Painting of Library Complex, Ikorodu Campus | LSP/W/NS/001/22 | 1 | 5,026,339.00 | <10M | NS | BOQ | POST | Plan | POST | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | NA | NA | NA |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
3 | Maintenance of office Building-plumbing works, electrical mtce, repartitioning of office space, replacement of window blind, mason work in offices, drycleaning of window blind, repair of deterioted buildings | LSP/W/NCB/001/22 | 1 | 95,249,919.96 | <100M | NCB | BOQ | POST | Plan | PRIOR | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
4 | Erection of Perimeter Fence on Ikorodu Campus Landscape (Erikorodo Axis) (ON-GOING) | [7 empty] | Plan
|  | LSP/W/NCB/004/20 | 1 | 17,944,436.11 | <100M | NS | BOQ | POST | Actual | PRIOR | [7 empty] | ON GOING
5 | Construction & Facilities of Fire Station on Ikorodu Campus (ON-GOING) | [7 empty] | Plan
|  | LSP/W/NCB/005/20 | 1 | 30,000,000.00 | <100M | NS | BOQ | POST | Actual | PRIOR | [7 empty] | ON GOING
6 | Construction of Administrative Block (ON-GOING) | [7 empty] | Plan
|  | LSP/W/ICB/006/20 | 1 | 1,000,000,000.00 | >100M | ICB | BOQ | POST | Actual | PRIOR | [7 empty] | ON GOING
7 | Motor Vehicle Repair & Maintenance - servicing and repair of saloon cars, utility buses, pick-up buses, coaster buses, tata buses, servicing & repair of lawn mower, vehicle maintenance | LSP/W-F/NS/001/22 | 1 | 24,455,000.00 | <100M | NS | BOQ | POST | Plan | PRIOR | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | NA
Actual
8 | Maintenance of Infrastructures (Laboratory & Lecture Room)- for maintenance of School laboratories, Workshops & Classroom, provision for staff quarters structure maintenance, to address roadnetwork, maintenance, maintenance/repair of students toilets, construction of ward ward robe cover for academic gown for store unit, access road & car park infrastructural improvement | LSP/W-F/NS/002/22 | 1 | 54,860,080.00 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | 03/06/22 | 01/07/22 | 01/07/22 |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
9 | Construction & Rehabilitation | LSP/W/NCB/003/22 | 1 | 139,736,540.00 | >100M | NCB | BOQ | POST | Plan | PRIOR | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
10 | ACCREDITATION - Construction/Refurbishment of Workshops and Laboratories in Fisheries Technology | LSP/W/NS/004/22 | 1 | 7,709,058.00 | <10M | NS | BOQ | POST | Plan |  | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | 03/06/22 | 01/07/22 | 01/07/22 |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
| TOTAL COST |  |  | 1374981373.07 |  |  |  |  | Plan
Actual

## NON PROC
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
Plan/Actual
S/N | Activity Description | Package Number | Budget Avail |  | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Transport & Travels- Rector and Registrar travel for CAPPA oversea meeting, Travel on official duties within the country by staff (non teaching/directorate and divisions), travel on academic assignment by teaching staff, transport allowance to staff on official assignment, transport allowance to teaching staff on official assignment | LSP/NP/NM/001/22 | 46583240 | Plan | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67
Actual
2 | General Utility Services - CUG Telephone subscription for officers, telephone monetisation for Principal Officers & P. A's, DSTV subscription for Principal Officers, DSTV Acquisition & installation-Poly Librarian, internet subscription expenses, (Moderm), imprest expenses on recharge card, electricity expenses & related charges, electricity expenses allowance for Principal officers | LSP/NP/NM/002/22 | 140,880,602.98 | Plan | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25
Actual
3 | Press, Public Relation Expenses - Provision for communial Donation & Gift to host community of Laspotech, Provision for donation & gifts to Internal & External Publics, provision for Gift and entertainment for monitoring activities of regulatory bodies, Gift provision for friends of the Polytechnic, festival celebration gift to Principal officers, Ileya gift provision to some selected Obas in Lagos State, other public relation activities within the Y2020, daily Newspapers & Journal, School/Departmental newspaper & Magazine expenses | LSP/NP/NM/003/22 | 45,097,160.00 | Plan | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66
Actual
4 | Bank Charges - Bank transaction charges | LSP/NP/NM/004/22 | 3,000,000.00 | Plan | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00
Actual
5 | Insurance Expenses- Group life Insurance Premium, Group Personal Accident Insurance Premium, provision for all Polytechnic Vehicle Insurance, provision for Fire & other Peril | LSP/NP/NM/005/22 | 193,920,000.00 | Plan | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00
Actual
6 | Special Academic Programmes-for Excursion/field visit of Schools to location within the country, admission exercise screening committee honorarium, publicity expenses on post UTME, UTME screening sending of SMS message, UTME Screening communication expenses, UTME Screening Logistic, Library Technical Books & Journals, Screening & verification fees, travel for screening of ND results of intending HND students, provision of screening of staff results, Ready set work initiative, external fairs & exhibition expenses | LSP/NP/NM/006/22 | 44,621,200.00 | Plan | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34
Actual
7 | Examination Administrative Expenses-- Provision for payment of Honorarium for 317 nos External Moderators for question moderators, vetting of script and project oral defence, honorarium for textbook assessment fee to external Assessors, honorarium to Interview Panelist engaged for annual staff promotion interview, admission/examination administration & related matters expenses | LSP/NP/NM/007/22 | 28,329,600.00 | Plan | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00
Actual
8 | Personnel Cost (Subvention) | LSP/NP/NM/008/22 | 3,526,076,924.00 | Plan | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67
Actual
9 | Professional Affiliation expenses-subscription due of the Polytechnic to CAPPA, ANSTI & COHEADS, Annual dues to COREG, Annual dues for SIWES to ITF, annual dues to BUSCON, annual dues to Coplin, subscription to E-Journal, E-Books, provision for membership registration & subscription to other clubs by principal officers, subscription to Professional body like ICAN & ANAN. | LSP/NP/NM/009/22 | 39,072,930.08 | Plan | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51
Actual
10 | Governing Council-- Regular & other Ad-hoc Committee meetings composition honorarium to council members, festival celebration gifts to Council members, provision for quarterly honorarium & percuniary allowance for council member, provision for milestone celebrations of council members,quarterly allowance for council members, fuel grant allowance to deputy registrar, car mtc allowance to DR council affairs | LSP/NP/NM/010/22 | 90,792,000.00 | Plan | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00
Actual
11 | ICT expenses - for annual IP Access subscription charge. | LSP/NP/NM/011/22 | 35,760,000.00 | Plan | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00
Actual
12 | Debt Obligation | LSP/NP/NM/012/22 | 186,278,600.00 | Plan | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66
Actual
13 | Meeting & Hospitality--prov. For monthly mgt committee meeting & Executive Mgt Committee secretariate expenses, support for student Union for annual week activities, transport & Accommodation support to attend NANS meeting within west zone, Laspo SUG orientation programme, SUG office running imprest, provision for non-accident bonus for W&S dept. drivers, drivers responsibilities allowances, honorarium for security officers for weekends work, honorarium for non-teaching administrative officers for worklate, weekend work, public holidays work, academic board & committee meeting expenses, honorarium for SIWES coordinators | LSP/NP/NM/013/22 | 49,752,400.00 | Plan | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33
Actual
14 | Research & Development | LSP/NP/NM/014/22 | 25,500,000.00 | Plan | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00
Actual
15 | Consultancy & Legal Expenses- Honorarium to chairman in-house legal committee | LSP/NP/NM/015/22 | 200,000.00 | Plan | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66
Actual
16 | Cleaning & Landscaping expenses-quarterly landscaping of the Polytechnic, disposal of campus waste inclusive medical waste- LAWMA. | LSP/NP/NM/016/22 | 6,278,688.00 | Plan | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00
Actual
17 | Procurement of Laboratory Reagent, Consumables & Teaching aid - Expense on students project exhibition and defence | LSP/NP/NM/017/22 | 5,824,000.00 | Plan | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33
Actual
18 | Security Expenses - Relation with external security agencies grant, operational intelligent grant, under cover security honorarium, emergency security expenses | LSP/NP/NM/018/22 | 75,324,000.00 | Plan | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00
Actual
19 | Special Duty expenses- welfare expenses, provision for revolving loan, transformation to University expenses | LSP/NP/NM/019/22 | 185,800,000.00 | Plan | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33
Actual
20 | Ceremonies - NIPOGA & WAPOGA games, senior staff games of Polytechnic, NIPOGA Host fee, Annual subscription to NIPOGA, Annual subscription to WAPOGA | LSP/NP/NM/020/22 | 35,840,000.00 | Plan | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66
Actual
| TOTAL COST |  | 4764931345.06

## CONSULTANCY
PROCUREMENT PLAN FOR CONSULTANCY SERVICES ®
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) | [6 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  |  | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1wk | 2wks | 2-4 wks | 1-2wks | 1-2wks | 0
1 | Consultancy Services- External auditors fee for Y2021 Financial record audit, pursuance of legal cases before the Polytechnic & other Administrative legal unit runnings | LSP/S-C/QCBS/001/22 | QCBS | Lump sum | 19000000 | PRIOR | Plan | 18/02/22 | 04/03/22 | 11/03/22 | 08/04/22 | 22/04/22 | 06/05/2021 | 03/06/22 | 18/06/22 | 01/07/22 | 08/07/22 | 22/07/22 | 15/08/22 | 02/09/22 | 02/09/22 |  | 16/09/22 | 30/09/22 | 28/10/22 | 11/11/22 | 25/11/22
Actual
2 | Review of Polytechnic Master Plan--On going | [5 empty] | Plan
|  | LSP/S-C/LC/002/21 | Least cost | Lump sum | 25,000,000.00 | PRIOR | Actual | [9 empty] | ON GOING | [8 empty] | on-going
| Total Cost |  |  |  | 44000000 | [16 empty] | #REF! | [5 empty] | #REF!

## NON CONSULTANCY
PROCUREMENT PLAN FOR NON-CONSULTANCY SERVICES
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  |  |  | BASIC DATA |  |  |  |  | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  |  | Plan vs. Actual |  |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail. in Naira | Approval Threshold | Procurement Method | Plan Vs Actual | Pre-or Post Qual |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening Date | Submission of Bid Evaluation Rpt | Minutes of Negotiation | PPA Issues Certificate of Compliance |  | Mr. Governor's Approval | Register Mr. Governor's Approval | Contract Amount in N'000 | Date Contract Signature | Mobilization/ Advance Payment | Complete Delivery/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1wk | 1-2 wks | Plan | 1-4wks | 48Hours | 0 | 4-6 wks | 2-4 wks | 2-8wks | 4WKS
1 | Cleaning & Landscaping expenses- for 160nos outsourced cleaners, 40nos outsourced gardners, fumigation expenses | LSP/S-NC/NCB/001/22 | 1 | Various | 130,336,152.96 | >100M | NCB | Plan | POST | PRIOR | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
2 | ICT expenses - ICT Infrastructure routine maintenance | LSP/S-NC/NS/002/22 | 1 | Various | 38,208,000.00 | <100M | NS | Plan | POST | POST | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | 18/06/22 | Plan | 15/07/22 | 15/07/22 |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
3 | Ceremonies -convocation ceremony expenses, tree planting event, aatendance of technical committee & board meeting IRO games, academic inaugural lecture, Production of Flex Banner, expenses on matriculation ceremonies, provision for orientation expenses (entertainment) | LSP/S-NC/NCB/003/22 | 1 | Various | 63,192,000.00 | <100M | NCB | Plan | POST | PRIOR | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
4 | Management Information System- maintenance charge for Registry, Bursary, Library and Audit Softwares, renewal of Kaspersky Antivirus, repair of printers | LSP/S-NC/NS/004/22 | 1 | Various | 6,286,384.00 | <10M | NS | Plan | POST | POST | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 18/06/22 | NA | Plan | NA | NA |  | 09/09/22 | 07/10/22 | 02/12/22 | 30/12/22
[8 empty] | Actual | [9 empty] | Actual
5 | Miscellaneous- Entertaiment during ACB, SESAPCO, JUSAPCO, Board of School Meeting, courier expense on transcript, postage of administrative correspondence, postage stamp provision, renewal of Polytechnic private mail bag, production of Staff ID | LSP/S-NC/NCB/005/22 | 1 | Various | 58,994,640.00 | <100M | NCB | Plan | POST | PRIOR | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
6 | Maintenance of Infrastructures (Laboratory & Lecture Room)- connection of ICT centre to the national grid | LSP/S-NC/NS/006/22 | 1 | Various | 5,592,408.00 | <10M | NS | Plan | POST | POST | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | NA | Plan | NA | NA |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
7 | Maintenance of Equipment & Machine -annual mtce of Risograph machine, mtce of office photocopier machine, repair & mtce of library complex PABX system, mtc of projectors, public address system, mtce agreement on xerox photocopier machine mtce of walkie talkie machine, annual renewal of fire arms, mtce of X-tray machine, mtce of spectrophotometer machine mtce of ultra sound machine, mtce provision gor office equipment, mtce of office cusshion chairs, mtce of various laboratory machines | LSP/S-NC/NS/007/22 | 1 | Various | 25,500,657.39 | <100M | NS | Plan | POST | POST | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
8 | Advertisement & Awareness Campaign - Publicity for HND admission, newspaper placement for UTME screening, weekly Polytechnic newsflash | LSP/S-NC/NS/008/22 | 1 | Various | 14063000 | <100M | NS | Plan | POST | PRIOR | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 18/06/22 | 01/07/22 | Plan | 29/07/22 | 29/07/22 |  | 09/09/22 | 07/10/22 | 02/12/22 | 30/12/22
[8 empty] | Actual | [9 empty] | Actual
9 | Security Expenses - provision for outsourced security operatives. | LSP/S-NC/NCB/009/22 | 1 | Various | 93366000 | <100M | NCB | Plan | POST | PRIOR | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
10 | Special Duty expenses-provision for enterprise resource packages (ERP), Financial Manual, special essential expenditure, school of Agric Farming project | LSP/S-NC/NCB/010/22 | 1 | Various | 306720000 | >100M | NCB | Plan | POST | PRIOR | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | 18/06/22 | Plan | 15/07/22 | 15/07/22 |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
11 | Fueling & Maintenance of expenses -Maintenance of Generator set | LSP/S-NC-F/NS/011/22 | 1 | Various | 38105600 | <100M | NS | Plan | POST | POST | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
12 | Motor Vehicle Repair & Maintenance - Car maintenance grant allowance, renewal of vehicles particulars | LSP/S-NC/NS/012/22 | 1 | Various | 14682000 | <100M | NS | Plan | POST | POST | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 18/06/22 | 01/07/22 | Plan | 29/07/22 | 29/07/22 |  | 09/09/22 | 07/10/22 | 02/12/22 | 30/12/22
[8 empty] | Actual | [9 empty] | Actual
13 | Conference & Seminars- Provision for Management Retreat & Council retreat | LSP/S-NC/NS/013/22 | 1 | Various | 18096000 | <100M | NS | Plan | POST | POST | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
14 | Press & Public Relation Expenses - Rector's quarterly press briefing expenses, External relation activities | LSP/S-NC/NS/014/22 | 1 | Various | 5054400 | <10M | NS | Plan | POST | POST | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | NA | Plan | NA | NA |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
15 | Consultancy & Legal Expenses- one set of Laws of the Federation & 12nos. Labour Law report, collaborations on entrepreneurship activities, entreprenuership practical facilitators | LSP/S-NC/NS/015/22 | 1 | Various | 11778100 | <100M | NS | Plan | POST | POST | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
16 | Examination Administrative Expenses--Printing of ID Card for students identification | LSP/S-NC/NS/016/22 | 1 | Various | 7800000 | <10M | NS | Plan | POST | POST | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 18/06/22 | NA | Plan | NA | NA |  | 09/09/22 | 07/10/22 | 02/12/22 | 30/12/22
[8 empty] | Actual | [9 empty] | Actual
17 | Governing Council--provision for milestone celebration of council member (birthday, direct offspring weeding, burial ceremonies of biological parents), entertainment/hospitality, maintenance of council Equipments | LSP/S-NC/NS/017/22 | 1 | Various | 12658400 | <100M | NS | Plan | POST | POST | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
18 | Health Care & Medical Expenses- Pre-registration medical screening expenses | LSP/S-NC/NS/018/22 | 1 | Various | 6000000 | <10M | NS | Plan | POST | POST | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | NA | Plan | NA | NA |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
19 | Erection of CCTV Camera on Ikorodu Campus | LSP/S-NC/NS/019/22 | 1 | Various | 17,854,086.90 | <100M | NS | Plan | POST | PRIOR | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
| TOTAL COST |  |  |  | 874287829.25 |  |  | Plan | [9 empty] | Plan |  |  | #REF!

## NILLED
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
S/N | Description of Training /Workshop/Conference | Objective of Training/Workshop/Conference | Package Number | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Conference & Seminar for Principal Officers | For training & development | LSP/S-WTC/SS/001/22 | 6 |  | Plan |  |  |  |  | 19,338,466.93
Actual
2 | Academic Staff Seminars & Conferences | For training & development | LSP/S-WTC/SS/002/22 | 185 |  | Plan |  |  |  |  | 61,859,164.69
Actual
3 | Non-teaching staff Seminars & Conferences | For training & development | LSP/S-WTC/SS/003/22 | 350 |  | Plan |  |  |  |  | 92,892,800.00
Actual
4 | General Staff training & Development for Service delivery | for staff training & development | LSP/S-WTC/SS/004/22 |  |  | Plan |  |  |  |  | 15,321,280.00
Actual
5 | WITED Conference | for training & development | LSP/S-WTC/SS/005/22 |  |  | Plan |  |  |  |  | 410,176.00
Actual
6 | MTSS Workshop Training | for training & development | LSP/S-WTC/SS/006/22 |  |  | Plan |  |  |  |  | 482,560.00
Actual
7 | Burscon Seminar | for training & development | LSP/S-WTC/SS/007/22 |  |  | Plan |  |  |  |  | 3,016,000.01
Actual
8 | Seminar support for Union Executives | for training & development | LSP/S-WTC/SS/008/22 |  |  | Plan |  |  |  |  | 3,016,000.01
Actual
9 | Hosting of COHEADS & BURSCON conference | for training & development | LSP/S-WTC/SS/009/22 |  |  | Plan |  |  |  |  | 5,803,200.00
Actual
| PLAN TOTAL |  |  |  |  | Plan |  |  |  |  | 202139647.64
| ACTUAL TOTAL |  |  |  |  | Actual

## NIL
PROCUREMENT PLAN FOR CONSULTANCY SERVICES ®
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) | [6 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  |  | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1wk | 2wks | 2-4 wks | 1-2wks | 1-2wks | 0
1 | Consultancy Services- External auditors fee for Y2021 Financial record audit, pursuance of legal cases before the Polytechnic & other Administrative legal unit runnings | LSP/S-C/QCBS/001/22 | QCBS | Lump sum | 19000000 | PRIOR | Plan | 18/02/22 | 04/03/22 | 11/03/22 | 08/04/22 | 22/04/22 | 06/05/2021 | 03/06/22 | 18/06/22 | 01/07/22 | 08/07/22 | 22/07/22 | 15/08/22 | 02/09/22 | 02/09/22 |  | 16/09/22 | 30/09/22 | 28/10/22 | 11/11/22 | 25/11/22
Actual
| Total Cost |  |  |  | 19000000 | [16 empty] | #REF! | [5 empty] | #REF!
.

## GOODS (2)
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  |  | BASIC DATA | [5 empty] | Plan/Actual | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail. in Naira | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hours | 0 | 1 wk | 1-2wks | 2-4 wks | 4wk
1 | Procurement of 10hp submersible pump, workshop tools & equipment, gun powder for fire arms (Maintenance of Equipment & Macihne) | LSP/G/NS/001/22 | 1 | Various | 4,600,000.00 | <10M | NS | POST | POST | Plan | 25/03/22 | 08/04/22 | 22/04/22 | 03/06/22 | 18/06/22 | NA | NA | NA |  | 05/08/22 | 19/08/22 | 16/09/22 | 14/10/22 | 17/10/22
Actual
2 | Procurement of Stationeries- Hardcover note book, A4 paper, Flat file, student file jacket, official envelop, black RZ ink, biros, staple pin, staple machine | LSP/G/NCB/002/22 | 1 | Various | 58,918,078.40 | <100M | NCB | POST | PRIOR | Plan | 18/02/22 | 04/03/22 | 18/03/22 | 29/04/22 | 13/05/22 | 27/05/22 | 25/06/22 | 25/06/22 |  | 01/07/22 | 15/07/22 | 12/08/22 | 09/09/22 | 2022-12-09
Actual
3 | Procurement of Uniform & Protective Outfit-production of academic gown, laboratory uniform, watchman uniform and cardigan, safety boat, raincoat for security personnel | LSP/G/NS/003/22 | 1 | 150 | 2,895,000.00 | <10M | NS | POST | POST | Plan | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | NA | NA | NA |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | 19/09/22
Actual
4 | Procurement of Laboratory Reagent, Consumables & Teaching aid - vacination, medication & vet expenses, procurement of Seedding, livestock & fish feeds, teaching aid and consumables | LSP/G/NCB/005/22 | 1 | Various | 101,953,600.00 | >100M | NCB | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | 2022-03-10
Actual
5 | Procurement of photocopy toner, laptop battery charger, APC Extension box, printers toner, Optical mouse, flash drive, Power pack, desktop harddrive, motherboard, power cable (Management Information System) | LSP/G/NS/006/22 | 1 | Various | 42,950,700.00 | <100M | NS | POST | PRIOR | Plan | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 25/06/22 | 22/07/22 | 22/07/22 |  | 29/07/22 | 12/08/22 | 09/09/22 | 07/10/22 | 2022-10-10
Actual
6 | Procurement of Medical Lab reagent, (chemicals, x-ray films, gloves), procurement of medical drugs from manufacturer for dispensing to students on needs basis (Health Care & Medical Expenses) | LSP/G/NS/007/22 | 1 | Various | 23,600,000.00 | <100M | NS | POST | PRIOR | Plan | 25/03/22 | 08/04/22 | 22/04/22 | 03/06/22 | 18/06/22 | 01/07/22 | 29/07/22 | 29/07/22 |  | 05/08/22 | 19/08/22 | 16/09/22 | 14/10/22 | 17/10/22
Actual
7 | Procurement of Chemical for weed weakening such as forceup & tools for park and Garden (Cleaning & Landscaping expenses) | LSP/G/NS/008/22 | 1 | Various | 24,842,188.80 | <100M | NS | POST | POST | Plan | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | 03/06/22 | 01/07/22 | 01/07/22 |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | 19/09/22
Actual
8 | Procurement of Fuel for Principal officer, School/departmental officers car, Fuelling of Utility Buses and other Polytechnic event (Motor Vehicle Fuel Consumption) | LSP/G-F/NS/001/22 | Lot 1 | Various | 96,836,892.80 | <100M | NS | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | 22/09/22
Actual
9 | Procurement of Fuel for Council Utility Bus (council utility bus fueling)-(Governing Council) | LSP/G-F/NS/002/22 | Lot 2 | Various | 7,820,800.00 | <10M | NS | POST | POST | Plan | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | NA | NA | NA |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | 26/09/22
Actual
10 | Procurement of bulb & door lock (Maintenance of office Building) | LSP/G-F/NS/003/22 | 1 | Various | 2,380,000.00 | <10M | NS | POST | POST | Plan | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | NA | NA | NA |  | 29/07/22 | 12/08/22 | 09/09/22 | 07/10/22 | 2022-10-10
Actual
11 | Procurement of tyres and batteries (Motor Vehicle Repair & Maintenance) | LSP/G-F/NS/004/22 | 1 | Various | 6,756,000.00 | <10M | NS | POST | POST | Plan | 25/03/22 | 08/04/22 | 22/04/22 | 03/06/22 | 18/06/22 | NA | NA | NA |  | 05/08/22 | 19/08/22 | 16/09/22 | 14/10/22 | 17/10/22
Actual
12 | Procurement of electrical maintenance materials needs to central store, Procurement of Electrical, Plumbing fitting, repairs and other sundry maintenance needs (Maintenance of Infrastructure (Laboratory & Lecture Room) | LSP/G-F/NS/005/22 | 1 | Various | 6,760,000.00 | <10M | NS | POST | POST | Plan | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | NA | NA | NA |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | 19/09/22
Actual
13 | Procurement of Diesel to Fuel Generators (Fuelling & Maintenance of Generators) | LSP/G-F/NCB/006/22 | 1 | 14 | 120,556,800.00 | >100M | NCB | POST | PRIOR | Plan | 11/03/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 18/06/22 | 15/07/22 | 15/07/22 |  | 22/07/22 | 05/08/22 | 02/09/22 | 30/09/22 | 2022-03-10
Actual
| TOTAL COST |  |  |  | 500870060 |  |  |  |  | Plan

## WORKS (2)
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  |  | BASIC DATA |  |  |  |  | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  |  |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | Budget Avail. in Naira | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qual |  |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governors Approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4wks | 48hrs | 0 | 1 wk | 1-2wks | 2-4 wks | 4wks
1 | Construction of School of Technology Complex at Ikorodu Campus (Block D)-- ON GOING | [7 empty] | Plan
|  | LSP/W/NCB/001/21 | 1 | 241,151,597.00 | >100M | NCB | BOQ | POST | Actual | PRIOR | [7 empty] | ON GOING
2 | Painting of Library Complex, Ikorodu Campus | LSP/W/NS/001/22 | 1 | 5,026,339.00 | <10M | NS | BOQ | POST | Plan | POST | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | NA | NA | NA |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
1 | Plumbing works, electrical mtce, repartitioning of office space, replacement of window blind, mason work in offices, drycleaning of window blind, repair of deterioted buildings (Maintenance of Buildings) | LSP/W-F/NCB/001/22 | 1 | 95,249,919.96 | <100M | NCB | BOQ | POST | Plan | PRIOR | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | 29/09/22
Actual
2 | Maintenance of School laboratories, Workshops & Classroom, provision for staff quarters structure maintenance, to address roadnetwork, maintenance/repair of students toilets, construction of ward robe cover for academic gown for store unit, access road & car park infrastructural improvement (Maintenance of Infrastructures- Laboratory & Lecture Rooms) | LSP/W-F/NS/002/22 | 1 | 54,860,080.00 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | 03/06/22 | 01/07/22 | 01/07/22 |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | 19/09/22
Actual
9 | Construction & Rehabilitation | LSP/W/NCB/003/22 | 1 | 139,736,540.00 | >100M | NCB | BOQ | POST | Plan | PRIOR | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 11/06/22 | 08/07/22 | 08/07/22 |  | 15/07/22 | 29/07/22 | 26/08/22 | 23/09/22 | NA
Actual
10 | ACCREDITATION - Construction/Refurbishment of Workshops and Laboratories in Fisheries Technology | LSP/W/NS/004/22 | 1 | 7,709,058.00 | <10M | NS | BOQ | POST | Plan |  | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/05/22 | 03/06/22 | 01/07/22 | 01/07/22 |  | 08/07/22 | 22/07/22 | 19/08/22 | 16/09/22 | NA
Actual
| TOTAL COST |  |  | 150109999.96 |  |  |  |  | Plan
Actual

## NON PROC (2)
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
Plan/Actual
S/N | Activity Description | Package Number | Budget Avail |  | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Transport & Travels Expenses- Rector and Registrar travel for CAPPA oversea meeting, Travel on official duties within the country by staff (non teaching/directorate and divisions), travel on academic assignment by teaching staff, transport allowance to staff on official assignment, transport allowance to teaching staff on official assignment | LSP/NP/NM/001/22 | 46583240 | Plan | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67 | 3,881,936.67
Actual
2 | General Utility Services - CUG Telephone subscription for officers, telephone monetisation for Principal Officers & P. A's, DSTV subscription for Principal Officers, DSTV Acquisition & installation-Poly Librarian, internet subscription expenses, (Moderm), imprest expenses on recharge card, electricity expenses & related charges, electricity expenses allowance for Principal officers | LSP/NP/NM/002/22 | 140,880,602.98 | Plan | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25 | 11,740,050.25
Actual
3 | Press, Public Relation Expenses - Provision for communial Donation & Gift to host community of Laspotech, Provision for donation & gifts to Internal & External Publics, provision for Gift and entertainment for monitoring activities of regulatory bodies, Gift provision for friends of the Polytechnic, festival celebration gift to Principal officers, Ileya gift provision to some selected Obas in Lagos State, other public relation activities within the Y2020, daily Newspapers & Journal, School/Departmental newspaper & Magazine expenses | LSP/NP/NM/003/22 | 45,097,160.00 | Plan | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66 | 3,758,096.66
Actual
4 | Bank Charges - Payment of Bank transaction charges | LSP/NP/NM/004/22 | 3,000,000.00 | Plan | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00 | 250,000.00
Actual
5 | Insurance Expenses- Payment of Group life Insurance Premium, Group Personal Accident Insurance Premium, provision for all Polytechnic Vehicle Insurance, provision for Fire & other Peril | LSP/NP/NM/005/22 | 193,920,000.00 | Plan | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00 | 16,160,000.00
Actual
6 | Special Academic Programmes-for Excursion/field visit of Schools to location within the country, admission exercise screening committee honorarium, publicity expenses on post UTME, UTME screening sending of SMS message, UTME Screening communication expenses, UTME Screening Logistic, Library Technical Books & Journals, Screening & verification fees, travel for screening of ND results of intending HND students, provision of screening of staff results, Ready set work initiative, external fairs & exhibition expenses | LSP/NP/NM/006/22 | 44,621,200.00 | Plan | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34 | 3,718,433.34
Actual
7 | Examination Administrative Expenses-- Provision for payment of Honorarium for 317 nos External Moderators for question moderators, vetting of script and project oral defence, honorarium for textbook assessment fee to external Assessors, honorarium to Interview Panelist engaged for annual staff promotion interview, admission/examination administration & related matters expenses | LSP/NP/NM/007/22 | 28,329,600.00 | Plan | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00 | 2,360,800.00
Actual
8 | Personnel Cost (Subvention) | LSP/NP/NM/008/22 | 3,526,076,924.00 | Plan | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67 | 293,839,743.67
Actual
9 | Professional Affiliation expenses-subscription due of the Polytechnic to CAPPA, ANSTI & COHEADS, Annual dues to COREG, Annual dues for SIWES to ITF, annual dues to BUSCON, annual dues to Coplin, subscription to E-Journal, E-Books, provision for membership registration & subscription to other clubs by principal officers, subscription to Professional body like ICAN & ANAN. | LSP/NP/NM/009/22 | 39,072,930.08 | Plan | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51 | 3,256,077.51
Actual
10 | Governing Council-- Regular & other Ad-hoc Committee meetings composition honorarium to council members, festival celebration gifts to Council members, provision for quarterly honorarium & percuniary allowance for council member, provision for milestone celebrations of council members,quarterly allowance for council members, fuel grant allowance to deputy registrar, car mtc allowance to DR council affairs (Honorarium) | LSP/NP/NM/010/22 | 90,792,000.00 | Plan | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00 | 7,566,000.00
Actual
11 | ICT expenses - Annual IP Access subscription charge. | LSP/NP/NM/011/22 | 35,760,000.00 | Plan | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00 | 2,980,000.00
Actual
12 | Payment of Debt Obligation | LSP/NP/NM/012/22 | 186,278,600.00 | Plan | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66
Actual
13 | Meeting & Hospitality--prov. For monthly mgt committee meeting & Executive Mgt Committee secretariate expenses, support for student Union for annual week activities, transport & Accommodation support to attend NANS meeting within west zone, Laspo SUG orientation programme, SUG office running imprest, provision for non-accident bonus for W&S dept. drivers, drivers responsibilities allowances, honorarium for security officers for weekends work, honorarium for non-teaching administrative officers for worklate, weekend work, public holidays work, academic board & committee meeting expenses, honorarium for SIWES coordinators | LSP/NP/NM/013/22 | 49,752,400.00 | Plan | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33 | 4,146,033.33
Actual
14 | Research & Development- grant for R&D | LSP/NP/NM/014/22 | 25,500,000.00 | Plan | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00 | 2,125,000.00
Actual
15 | Consultancy & Legal Expenses- Honorarium to chairman in-house legal committee | LSP/NP/NM/015/22 | 200,000.00 | Plan | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66
Actual
16 | Cleaning & Landscaping expenses-quarterly landscaping of the Polytechnic, disposal of campus waste inclusive medical waste- LAWMA. | LSP/NP/NM/016/22 | 6,278,688.00 | Plan | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00 | 523,224.00
Actual
17 | Procurement of Laboratory Reagent, Consumables & Teaching aid - Expense on students project exhibition and defence | LSP/NP/NM/017/22 | 5,824,000.00 | Plan | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33 | 485,333.33
Actual
18 | Security Expenses - Relation with external security agencies grant, operational intelligent grant, under cover security honorarium, emergency security expenses | LSP/NP/NM/018/22 | 75,324,000.00 | Plan | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00 | 6,277,000.00
Actual
19 | Special Duty expenses- welfare expenses, provision for revolving loan, transformation to University expenses | LSP/NP/NM/019/22 | 185,800,000.00 | Plan | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33 | 15,483,333.33
Actual
20 | Ceremonies - NIPOGA & WAPOGA games, senior staff games of Polytechnic, NIPOGA Host fee, Annual subscription to NIPOGA, Annual subscription to WAPOGA | LSP/NP/NM/020/22 | 35,840,000.00 | Plan | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66 | 2,986,666.66
Actual
21 | SPTS Expenditure | LSP/NP/NM/021/22 | 1,126,132,743.00 | Plan | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25 | 93,844,395.25
Actual
| TOTAL COST |  | 5891064088.06

## CONSULTANCY (3)
PROCUREMENT PLAN FOR CONSULTANCY SERVICES ®
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) | [6 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  |  | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1wk | 2wks | 2-4 wks | 1-2wks | 1-2wks | 0
1 | Engagement of External auditors for Y2021 Financial record audit, pursuance of legal cases before the Polytechnic & other Administrative legal unit runnings (Consultancy Services) | LSP/S-C/QCBS/001/22 | QCBS | Lump sum | 19000000 | PRIOR | Plan | 18/02/22 | 04/03/22 | 11/03/22 | 08/04/22 | 22/04/22 | 06/05/2021 | 03/06/22 | 18/06/22 | 01/07/22 | 08/07/22 | 22/07/22 | 15/08/22 | 02/09/22 | 02/09/22 |  | 16/09/22 | 30/09/22 | 28/10/22 | 11/11/22 | 25/11/22
Actual
| Total Cost |  |  |  | 19000000 | [16 empty] | #REF! | [5 empty] | #REF!

## NON CONSULTANCY (2)
PROCUREMENT PLAN FOR NON-CONSULTANCY SERVICES
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  |  |  | BASIC DATA |  |  |  |  | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  |  | Plan vs. Actual |  |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail. in Naira | Approval Threshold | Procurement Method | Plan Vs Actual | Pre-or Post Qual |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening Date | Submission of Bid Evaluation Rpt | Minutes of Negotiation | PPA Issues Certificate of Compliance |  | Mr. Governor's Approval | Register Mr. Governor's Approval | Contract Amount in N'000 | Date Contract Signature | Mobilization/ Advance Payment | Complete Delivery/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1wk | 1-2 wks | Plan | 1-4wks | 48Hours | 0 | 4-6 wks | 2-4 wks | 2-8wks | 4WKS
1 | Outsourced of 160nos cleaners, 40nos outsourced gardners, fumigation expenses (Cleaning & Landscaping expenses) | LSP/S-NC/NCB/001/22 | 1 | Various | 130,336,152.96 | >100M | NCB | Plan | POST | PRIOR | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
2 | ICT Infrastructure routine maintenance-Maintenance of Server(ICT Expenses) | LSP/S-NC/NS/002/22 | 1 | Various | 38,208,000.00 | <100M | NS | Plan | POST | POST | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | 18/06/22 | Plan | 15/07/22 | 15/07/22 |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
3 | Convocation ceremony expenses, tree planting event, attendance of technical committee & board meeting IRO games, academic inaugural lecture, Production of Flex Banner, expenses on matriculation ceremonies, provision for orientation expenses (entertainment)(Ceremonies) | LSP/S-NC/NCB/003/22 | 1 | Various | 63,192,000.00 | <100M | NCB | Plan | POST | PRIOR | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
4 | Maintenance charge for Registry, Bursary, Library and Audit Softwares, renewal of Kaspersky Antivirus, repair of printers (Management Information System) | LSP/S-NC/NS/004/22 | 1 | Various | 6,286,384.00 | <10M | NS | Plan | POST | POST | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 18/06/22 | NA | Plan | NA | NA |  | 09/09/22 | 07/10/22 | 02/12/22 | 30/12/22
[8 empty] | Actual | [9 empty] | Actual
5 | Entertaiment during ACB, SESAPCO, JUSAPCO, Board of School Meeting, courier expense on transcript, postage of administrative correspondence, postage stamp provision, renewal of Polytechnic private mail bag, production of Staff ID (Miscellaneous) | LSP/S-NC/NCB/005/22 | 1 | Various | 58,994,640.00 | <100M | NCB | Plan | POST | PRIOR | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
6 | Maintenance of ICT network cable from ICT centre to the national grid (Maintenance of Infrastructure (Laboratory & Lecture Room) | LSP/S-NC/NS/006/22 | 1 | Various | 5,592,408.00 | <10M | NS | Plan | POST | POST | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | NA | Plan | NA | NA |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
7 | Annual mtce of Risograph machine, mtce of office photocopier machine, repair & mtce of library complex PABX system, mtc of projectors, public address system, mtce agreement on xerox photocopier machine mtce of walkie talkie machine, annual renewal of fire arms, mtce of X-tray machine, mtce of spectrophotometer machine mtce of ultra sound machine, mtce provision for office equipment, mtce of office cusshion chairs, mtce of various laboratory machines (Maintenance of Equipments & Machine) | LSP/S-NC/NS/007/22 | 1 | Various | 25,500,657.39 | <100M | NS | Plan | POST | POST | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
8 | Publicity for HND admission, newspaper placement for UTME screening, weekly Polytechnic newsflash (Advertisement & Awareness Campaign) | LSP/S-NC/NS/008/22 | 1 | Various | 14063000 | <100M | NS | Plan | POST | PRIOR | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 18/06/22 | 01/07/22 | Plan | 29/07/22 | 29/07/22 |  | 09/09/22 | 07/10/22 | 02/12/22 | 30/12/22
[8 empty] | Actual | [9 empty] | Actual
9 | Provision for outsourced security operatives (Security Expenses) | LSP/S-NC/NCB/009/22 | 1 | Various | 93366000 | <100M | NCB | Plan | POST | PRIOR | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
10 | Provision for enterprise resource packages (ERP), Financial Manual, special essential expenditure, school of Agric Farming project (Special Duty Expenses) | LSP/S-NC/NCB/010/22 | 1 | Various | 306720000 | >100M | NCB | Plan | POST | PRIOR | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | 18/06/22 | Plan | 15/07/22 | 15/07/22 |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
11 | Maintenance of Generator Set -Fueling & Maintenance of expenses | LSP/S-NC-F/NS/011/22 | 1 | Various | 38105600 | <100M | NS | Plan | POST | POST | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
12 | Motor Vehicle Repair & Maintenance - Car maintenance allowance, renewal of vehicles particulars | LSP/S-NC/NS/012/22 | 1 | Various | 14682000 | <100M | NS | Plan | POST | POST | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 18/06/22 | 01/07/22 | Plan | 29/07/22 | 29/07/22 |  | 09/09/22 | 07/10/22 | 02/12/22 | 30/12/22
[8 empty] | Actual | [9 empty] | Actual
13 | Provision for Management Retreat & Council retreat (Conference & Seminars) | LSP/S-NC/NS/013/22 | 1 | Various | 18096000 | <100M | NS | Plan | POST | POST | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
14 | Press & Public Relation Expenses - Rector's quarterly press briefing expenses, External relation activities | LSP/S-NC/NS/014/22 | 1 | Various | 5054400 | <10M | NS | Plan | POST | POST | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | NA | Plan | NA | NA |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
15 | Collaborations on entrepreneurship activities, entreprenuership practical facilitators one set of Laws of the Federation & 12nos. Labour Law report (Consultancy & Legal Expenses) | LSP/S-NC/NS/015/22 | 1 | Various | 11778100 | <100M | NS | Plan | POST | POST | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
[8 empty] | Actual | [9 empty] | Actual
16 | Printing of ID Card for students identification (Examination Administrative Expenses) | LSP/S-NC/NS/016/22 | 1 | Various | 7800000 | <10M | NS | Plan | POST | POST | 18/03/22 | 01/04/22 | 15/04/22 | 27/05/22 | 11/06/22 | 18/06/22 | NA | Plan | NA | NA |  | 09/09/22 | 07/10/22 | 02/12/22 | 30/12/22
[8 empty] | Actual | [9 empty] | Actual
17 | Provision for milestone celebration of council member (birthday, direct offspring weeding, burial ceremonies of biological parents), entertainment/hospitality, maintenance of council Equipments (Governing Council) | LSP/S-NC/NS/017/22 | 1 | Various | 12658400 | <100M | NS | Plan | POST | POST | 25/02/22 | 11/03/22 | 25/03/22 | 06/05/22 | 20/06/22 | 27/05/22 | 11/06/22 | Plan | 08/07/22 | 08/07/22 |  | 19/08/22 | 16/09/22 | 11/11/22 | 2022-09-12
[8 empty] | Actual | [9 empty] | Actual
18 | Pre-registration medical screening expenses (Health care & Medical Expenses) | LSP/S-NC/NS/018/22 | 1 | Various | 6000000 | <10M | NS | Plan | POST | POST | 04/03/22 | 18/03/22 | 01/04/22 | 13/05/22 | 27/05/22 | 03/06/22 | NA | Plan | NA | NA |  | 26/08/22 | 23/08/22 | 18/11/22 | 16/12/22
[8 empty] | Actual | [9 empty] | Actual
19 | Printing of seasonal publication (Calendar), EED Logbook, EED textbook, SIWES log book, Answer sheets, academic certificate (Printing & Production Expenses) | LSP/S-NC/NCB/019/22 | 1 | Various | 137,513,818.00 | >100M | NCB | Plan | POST | PRIOR | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
Actual
20 | Servicing and repair of saloon cars, utility buses, pick-up buses, coaster buses, tata buses, servicing & repair of lawn mower, vehicle maintenance (Motor Vehicle Repair & Maintenance) | LSP/W-F/NS/001/22 | 1 | Various | 24,455,000.00 | <100M | NS | Plan | POST | POST | 11/04/22 | 25/03/22 | 08/04/22 | 20/05/22 | 03/06/22 | 11/06/22 | 25/06/22 | Plan | 22/07/22 | 22/07/22 |  | 02/09/22 | 30/09/22 | 25/11/22 | 23/12/22
| TOTAL COST |  |  |  | 1018402560.35 |  |  | Plan | [9 empty] | Plan |  |  | #REF!

## SEMINAR (2)
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2022
S/N | Description of Training /Workshop/Conference | Objective of Training/Workshop/Conference | Package Number | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Conference & Seminar for Principal Officers | For training & development | LSP/S-WTC/SS/001/22 | 6 |  | Plan |  |  |  |  | 19,338,466.93
Actual
2 | Academic Staff Seminars & Conferences | For training & development | LSP/S-WTC/SS/002/22 | 185 |  | Plan |  |  |  |  | 61,859,164.69
Actual
3 | Non-teaching staff Seminars & Conferences | For training & development | LSP/S-WTC/SS/003/22 | 350 | 3-5 Days | Plan |  |  |  |  | 92,892,800.00
Actual
4 | General Staff training & Development for Service delivery | for staff training & development | LSP/S-WTC/SS/004/22 | 4 | 3-5 Days | Plan |  |  |  |  | 15,321,280.00
Actual
5 | WITED Conference | for training & development | LSP/S-WTC/SS/005/22 | 1 | 3-5 Days | Plan |  |  |  |  | 410,176.00
Actual
6 | MTSS Workshop Training | for training & development | LSP/S-WTC/SS/006/22 | 2 | 3-5 Days | Plan |  |  |  |  | 482,560.00
Actual
7 | Burscon Seminar | for training & development | LSP/S-WTC/SS/007/22 | 4 | 5 days | Plan |  |  |  |  | 3,016,000.01
Actual
8 | Seminar support for Union Executives | for training & development | LSP/S-WTC/SS/008/22 | 3 | 3-5 Days | Plan |  |  |  |  | 3,016,000.01
Actual
9 | Hosting of COHEADS & BURSCON conference | for training & development | LSP/S-WTC/SS/009/22 | 1 | 5 days | Plan |  |  |  |  | 5,803,200.00
Actual
| PLAN TOTAL |  |  |  |  | Plan |  |  |  |  | 202139647.64
| ACTUAL TOTAL |  |  |  |  | Actual