## GOODS
PROCUREMENT PLAN FOR GOODS
| MINISTRY/ AGENCY: OFFICE OF CHIEF OF STAFF | [19 empty] | s
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION | Lot Number | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number |  | No. of Unit | Budget Avail | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | Notification of Award | Date Contract Signature | Mobilization/ Advance Payment | Complete Delivery/Istall | Inspection and Final Acceptance
[5 empty] | 0 | 0 |  |  |  | Plan | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4 wks | 48hrs | 0 |  | 4-6 wks | 2-4 wks
Actual
1 | Procurement of Stationery
| Procurement of 1,200 Cartons of A4 Papers= N20,000,000 , Procurement of 650 Cartons of Fullscap Paper= N12,000,000, Procurement of 200cartons of minuiting sheet= N3,000,000 ; Procurement of 1000bin card = N1,000,000; Procurement of 109 Cartons ledger sheets N2,180,000; Procurement of 10cartons hard cover notebooks= N300,000; Procurement of 50 Stamps Pad= N25,000 , Procurement of endorsing ink =N495,000, Procurement of celltapes,Pencils, Biro, Pen, Lightpens,Calculators, Envelopes, file jackets,Ctn envelopes (various) and other office tools needed for use in the Office of Chief of Staff- N11,250,000 | OCOS/G-F/NS/001/2022 - Framework | NA |  | 50000000 | <100M | NS | Post | Prior | Plan | 5/01/22 | 2022-01-25 | 2022-02-08 | 22/.2.22 | 7/3/22 | 22/3/22 | 5/4/22 | 11/4/22 | 50000000 |  | 26/4/22 | 2022-05-04 | 18/5/21 | 2022-05-24
Actual
Uniform & Protective Outfits
| Raincoats Coats, Boots, 2 pairs of uniforms for the Drivers and Dispatch Riders, Petrol Attendants Domestic Staff , Cleaners and Mr. Governors Drivers.Procurement of Raincoats &Rainboots for catering staff in Lagos House= N2,000,000, Procurement of Rainboots for DSS Operatives= N2,800,000, Procurementof Uniforms for Cleaners, Gardners, Security and Lift Operators= N1,960,000, Procurement of Protective Outfits such as raincoat=N3,189,400, Procurement of Umbrellas for Drivers and Riders= N550,000,Procurement of 20 Motorbikes Helmets= N1,500,600 | OCOS/G/NS/002/2022 | NA |  | 12000000 | <50M | NS | Post | Post | Plan | 10/1/22 | 3/2/22 | 17/2/22 | 2/3/22 | 17/3/22 | 31/3/22 | 14/4/22 | 18/4/22 | 12000000 |  | 28/4/22 | 2022-05-12 | 19/5/22 | 2022-05-27
[10 empty] | Actual | [14 empty] | 0
Printing
| Printing of Invitation and Programmes for State Occasions and Special Cards for Eminent Citicizens, Printing of Letter Heads, Envelopes & Memo, invitation & Complimentary cards for Political Executives and Management Staff=N2,100,000, Production of Premium Birthday Cards for Political Executives, Eminient Citizens & Management Staff= N1,100,000 | OCOS/G/NS/003/2022 | 1 |  | 3200000 | <10M | NS | Post | Post | Plan | 18/1/22 | 10/2/22 | 24/2/22 | 9/3/22 | 24/3/22 | 7/4/22 | 21/4/22 | 25/4/22 | 3200000 |  | 3/5/22 | 2022-05-19 | 2/6/22 | 2022-06-08
Actual
Clothing of Security Personnel
| Procurement of uniforms for Officers of Nigerian Police =N3,500,000, State Security Services (SSS) =N 3,000,000, Spies attached to the Government Houses and other State Government Facilities =N3,500,000 | OCOS/G/NS/004/22 | 1 |  | 10000000 | <50M | NS | Post | Post | Plan | 25/1/22 | 17/2/22 | 2/3/22 | 16/3/22 | 31/3/22 | 11/4/22 | 25/4/22 | 37/4/22 | 10000000 |  | 13/5/22 | 2022-05-27 | 2/6/22 | 2022-06-09
Actual
Speech Writer and Protocol Unit Expences
| Procurement of Speech Jackets =N2,000,000, books =N3,000,000, past speeches of renowed Personalities = N4,000,000, and other Stationery items for use of the Speech Department=N3,000,000 | OCOS/G/NS/005/22 | 1 |  | 12000000 | <50M | NS | Post | Post | Plan | 3/2/22 | 2022-02-16 | 7/3/22 | 21/3/22 | 4/4/22 | 14/4/22 | 29/4/21 | 3/5/22 | 12000000 |  | 13/5/22 | 2022-05-27 | 2/6/22 | 2022-06-09
Actual
Chemical and Reagents
| Provision of Water Treatment Chemicals for the Plant at Marina = N400,000.00, Isaac John= N400,000.00, Ikeja=N800,000.00 &Parkview=N 400,000.00 | OCOS/G/NS/006/22 | 1 |  | 2000000 | <10M | NS | Post | Post | Plan | 3/2/22 | 2022-02-16 | 7/3/22 | 21/3/22 | 4/4/22 | 14/4/22 | 29/4/21 | 3/5/22 | 2000000 |  | 13/5/22 | 2022-05-27 | 2/6/22 | 2022-06-09
Actual
Procurement of Sports Equipment
| Procuement of Sports Equipment wears and Protective Kits for Footballers | OCOS/G/NS/007/22 | 1 |  | 2500000 | <10M | NS | Post | Post | Plan | 3/2/22 | 2022-02-16 | 7/3/22 | 21/3/22 | 4/4/22 | 14/4/22 | 29/4/21 | 3/5/22 | 2500000 |  | 13/5/22 | 2022-05-27 | 2/6/22 | 2022-06-09
Actual
.
| Total Cost |  |  |  | 91700000 |  |  |  |  | Plan | [8 empty] | 91700000
Actual
`
8]

## Non Consulting
PROCUREMENT PLAN FOR NON CONSULTING
MINISTRY/ AGENCY: OFFICE OF CHIEF OF STAFF
| BUDGET YEAR: | 2022
1 |  |  | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  |  | Plan/ Actual | APPROVAL |  | CONTRACT FINALIZATION (DATES)
| Contract Description | Package Number | Lot No | No. of Unit | Budget Avail | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Minute of Negotiation |  | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | Notification of Award | Date Contract Signature | Mobilization/ Advance Payment | Complete Delivery/Istall | Inspection and Final Acceptance
[5 empty] | 0 | 0 |  |  |  | Plan | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1wk | Plan | 1-2 wks | 1-2 wks | 0 |  | 4-6 wks | 2-4 wks
[10 empty] | Actual | [7 empty] | Actual
Maintenanace of Office Building
| Maintenance of Offices Such as Press Centre, Speech Villa and L-Wing Extension of the Round House as well asrepair and replacement of Offices 1200 Keys Locks @ N2,500 = N3,000,000.0. Repairs of 358 Doors @ N12,500= N4,475.000, Plumbing and Aluminium Material (bath mixer tape,basin tape bottle trap,WC Stop Clock,Kitchen Tap, Flushing Handle, Urine Tap etc.)= N10,085,000 - Repairs of 185 Slide Windows= N2,150,000.00 - Maintenance and Painting of Administrative Block Offices = N10,290,000.00 | OCOS/NC/NS/001/22 |  |  | 30000000 | <50M | NS | Post | Prior | Plan | 6/01/22 | 2022-01-27 | 2022-02-10 | 24/02.22 | 9/3/22 | 24/3/22 | 30/3/22 | Plan | 5/4/22 | 6/4/22 | 30000000 |  | 20/4/22 | 2022-05-04 | 18/5/22 | 2022-05-25
[10 empty] | Actual | [7 empty] | Actual
Motor Vehicles Repairs and Maintenance
| Replacement of Tyres,Tubes, Batteries and Service Charge to Vehicles attached to Mr. Governor, Chief of Staff, Permanent Secretary, Marina Lagos House, Ikeja Lagos House and Other Departments. - Servicing of 170 Vehivles @ 50,000 Per Every 2 Months = N8,500,000 X 6= N51,000,000, Replacement of Tyres 265/70/15RM = 100 tyres @ N55,000 =N5,500,000,Replacement of Tyres 700/70/16RM = 100 tyres @ N90,000 =N9,000,000,Replacement of Tyres 195/15CRM = 100 tyres @ N55,000 =N5,500,000,Replacement of Tyres 215/70/16RM = 100 tyres @ N55,000 =N5,500,000,Replacement of Tyres 265/60/18RM = 80 tyres @ N65,000 =N5,200,000,Replacement of Batteries 80Ahms = 100 @ N40,000 = N4,000,000, Lagos State Drivers Institute (LASDRI) Certificate for 87 Drivers = N212,000 (Annual), Renewal of Vehicle Licence for 170 Vehicles = N1,335,500 (Annual),Renewal of Road Worthiness for 170 Vehicles = N1,465,700 (Annual), Installation of Siren on pick up vans =N1,286,800 | OCOS/NC/NS/002/22 |  |  | 90000000 | <100M | NS | Post | Post | Plan | 13/1/22 | 3/2/22 | 17/2/22 | 2/3/22 | 17/3/22 | 31/3/22 | 5/4/22 | Plan | 12/4/22 | 14/4/22 | 90000000 |  | 28/4/22 | 2022-05-12 | 19/5/22 | 2022-05-26
|  |  | 4 | [6 empty] | Actual | [5 empty] | 1 |  | Actual
Motor Vehicle Fuel Consumption
| fuelling of 115 Official Vehicles, funds expended on consumption of weekly fuelling of 115 vehicles @N165.00 X 80ltrs per week X 52weeks = N78,936,000, purchase of 20cartons of engine & gear oils =N1,064,000 | OCOS/NC/NS/003/22 |  |  | 80000000 | <100M | NS | Post | Post | Plan | 20/1/22 | 10/2/22 | 24/2/22 | 9/3/22 | 24/3/22 | 7/4/22 | 14/4/22 | Plan | 20/4/22 | 21/4/22 | 80000000 |  | 6/5/22 | 2022-05-19 | 2/6/22 | 2022-06-09
[10 empty] | Actual | [7 empty] | Actual
MISCELLENOUS
| To be utilised to augement expenditure items with insufficient funds or unforeseen expenditure. (N8,000,000 per month X 12 months) =N96,000,000 | OCOS/NC/NS/004/22 |  |  | 96000000 | <100M | NS | Post | Post | Plan | 26/1/22 | 17/2/22 | 2/3/22 | 16/3/22 | 29/3/22 | 8/4/22 | 14/4/22 | Plan | 30/4/22 | 31/4/22 | 96000000 |  | 12/5/22 | 2022-05-26 | 2/6/22 | 2022-06-09
[10 empty] | Actual | [7 empty] | Actual
Upkeep /Maintenance Allowance
| Proposed expense to be incurred by maintennance Department, Medical Department & Catering Unit- Feeding of 378 security personnel @ N1,500 daily x 365days = N206,955,000 procurement of drug and medical kits =N95,000,000- maintenance of fountain and horticulture of (1) Lagos House, Marina =39,907,555.15, (2) Government House, Ayoola Coker = N5,000,000 (3)Government House, Parkview =N7,500,000 (4) Government House (Ikoyi/VI) =N7,500,000 (5) Lagos House, Ikeja N28,109,518.85 | OCOS/NC/NCB/005/22 |  |  | 389972074 | <500M | NCB | Post | Prior | Plan | 10/2/22 | 24/2/22 | 10/3/22 | 24/3/22 | 7/4/22 | 20/4/22 | 26/4/22 | Plan | 4/5/22 | 5/5/22 | 389972074 |  | 19/5/22 | 2022-06-02 | 16/6/22 | 2022-06-23
[10 empty] | Actual | [7 empty] | Actual
Fuel Dump
| maintenance/repair work at Alausa fuel dump = 3,320,000 and the 12-nos, Fuel pumps at Marina =N2,080,000, Lagos House Ikeja = N2,440,000. expenses on Renewal of Operating License = N3,160,000. | OCOS/NC/NS/006/22 |  |  | 11000000 | <50M | NS | Post | Post | Plan | 10/2/22 | 24/2/22 | 10/3/22 | 24/3/22 | 7/4/22 | 20/4/22 | 26/4/22 | Plan | 4/5/22 | 5/5/22 | 11000000 |  | 19/5/22 | 2022-06-02 | 16/6/22 | 2022-06-23
[10 empty] | Actual | [7 empty] | Actual
Maintenance and Repairs (Plant and Machines
| periodic servicing & Maintenace of Gen. Set located at:Lagos House Ikeja (5nos x N100,000 x 12months) = N6,000,000, Lagos House Marina (5nos x N100,000 x 12months) = N6,000,000, L-Wing (1no x N83,333.33 x 12months) = N1,000,000, Fuel Dump- 150KVA (5nos x N100,000 each x 12months) = N6,000,000. | OCOS/NC/NS/007/22 |  |  | 19000000 | <50M | NS | Post | Post | Plan | 17/2/22 | 3/3/22 | 17/3/22 | 4/4/22 | 14/4/22 | 28/4/22 | 3/5/22 | Plan | 11/5/22 | 12/5/22 | 19000000 |  | 26/5/22 | 2022-06-02 | 16/6/22 | 2022-06-23
[10 empty] | Actual | [5 empty] | ` |  | Actual
Maintenance of Boreholes & Traetment Plant
| Servicing and Maintenance of Boreholes and treatment plant at the Following Government Houses and Establishment: Marina (4 boreholes and 1 Treatment Plant) = N150,000, Parkview (4 boreholes and 1 Treatment Plant) = N100,000,Ayoola Coker (1 borehole) = N50,000, L-wing Office of round house (1 borehole) = N50,000, Oduduwa (2 borehole)= N70,000, Bourdillion (2 borehole) =N70,000, Abraham Adesanya (2 Borehole) =N70,0000, Mopol 49 Akodo (5 borholes) =N70,000, Oko Oba RRS Camp (2 borehole) =N70,000, Fuel Dump (2 borehole) =N50,000 RRS Hq Alausa( 1 Borehole)=N50,000. | OCOS/NC/NS/008/22 |  |  | 800000 | <10M | NS | Post | Post | Plan | 13/1/22 | 3/2/22 | 17/2/22 | 2/3/22 | 17/3/22 | 31/3/22 | 5/4/22 | Plan | 12/4/22 | 14/4/22 | 800000 |  | 28/4/22 | 2022-05-12 | 19/5/22 | 2022-05-26
[10 empty] | Actual | [7 empty] | Actual
Maintenance and Repairs of Computers
| Maintenance of Desktop Computers = N2,500,000: Procurement of Toners black,white) and colour inks for Printers =N3,500,000, Provision of Internet Network accessories =N10,000,000, replacement damaged keyboards, UPS battries, Flash drieves, Mouse, USB cables=N2,500,000 and maintenance of Laptops = N1,500,000. | OCOS/NC/NS/009/22 |  |  | 20000000 | <50M | NS | Post | Post | Plan | 27/1/22 | 17/2/22 | 2/3/22 | 16/3/21 | 31/3/22 | 6/4/22 | 14/4/22 | Plan | 28/4/22 | 29/4/22 | 20000000 |  | 12/5/22 | 2022-05-26 | 2/6/22 | 2022-06-09
[10 empty] | Actual | [7 empty] | Actual
ENTERTAINMENT
| Entertainment of VIP Guests, including Local and International Visitors of the Executive Governor Funds Expenses on Quarterly Hosting of Community Sensitization / Interaction of Political Pressure for= N43,777,157, Fund Expenses on Servicing of Lagos Monthly Praise Worship with the First Family for 12 Months - N1,606 x 12= N19, 272,000 , Funds expenses on Monthly Servicing of Security meetngs = N2,285,700 , Expenses incurred for hosting of the EID-el Kabir celebration Festival = N10,000,000) - Expenses incurred for hosting of the Christmas celebration Festival = N10,000,000), Expenses incurred for hosting of the Easter celebration = N10,000,000), Expenses incurred for hosting of the EID-el Fitri celebration Festival = N10,000,000), Expenses incurred for hosting various events, Meetings and Programmes= N6,665,143 = N10,000,000) | OCOS/NC/NS/010/22 |  |  | 113000000 | <500M | NS | Post | Prior | Plan | 6/01/22 | 2022-01-27 | 2022-02-10 | 24/02.22 | 9/3/22 | 24/3/22 | 30/3/22 | Plan | 5/4/22 | 6/4/22 | 113000000 |  | 20/4/22 | 2022-05-04 | 18/5/22 | 2022-05-25
[10 empty] | Actual | [7 empty] | Actual
ELECTRICAL EQUIPMENT
| Mechanical & Electrical appliance installed at the Lagos House, Lagos HouseMarina and the L-Wing annex of office of the Chief of Staff- Quarterly expense @rate pof 4,000,000/qrt = N16,000,000 | OCOS/GNCS/NS/011/22 |  |  | 16000000 | <100M | NS | Post | Prior | Plan | 6/01/22 | 2022-01-27 | 2022-02-10 | 24/02.22 | 9/3/22 | 24/3/22 | 30/3/22 | Plan | 5/4/22 | 6/4/22 | 16000000 |  | 20/4/22 | 2022-05-04 | 18/5/22 | 2022-05-25
[10 empty] | Actual | [7 empty] | Actual
RUNNING COST
| (1.) conduct of Special Assisgnments on behalf of H.E and other incidental expenses = N30,000,000 (2.) processing of passports, visas and arrangement of flight for top government functionaries =N30,000,000, and payment of wardrobe allowances to protocol officers = 10,000,000, (3) Running cost expenses of the office =N10,000,000. | OCOS/NC/NS/012/22 |  |  | 80000000 | <100M | NS | Post | Prior | Plan | 27/1/22 | 17/2/22 | 2/3/22 | 16/3/21 | 31/3/22 | 6/4/22 | 14/4/22 | Plan | 28/4/22 | 29/4/22 | 80000000 |  | 12/5/22 | 2022-05-26 | 2/6/22 | 2022-06-09
[10 empty] | Actual | [7 empty] | Actual
SPECIAL EXPENSES
| (1). First Baby of the year=N20,000,000. (2). New Year Annual Thanksgiving=N150,000,000. (3). Visitation to Senior Citizens=N97,000,000. (4). Community Sensitization/Elders' Visitation =N40,000,000. (5). Esater Family Fiesta=N30,000,000 (6). Ramadan Tafsir=N30,000,000, (7). Eid-El-Fitir Festival =N45,000,000, (8). Eid-El-Kabir Festival=N43,000,000, (9). Annual Christmas/Children Party= N70,500,000, (10).Lagos Praise-Worship=N23,760,000, (11). One Day Governor=N5,000,000. (12). Sexual Gender Based Violence=N15,000,000. (13). My Boy Child=N20,000,000. (14). Muslim Sister Seminar=N35,000,000, and Youth Collaboration, Lagos Mega Praise COWLSO Monthly Meeting. | OCOS/NC/NS/012/22 |  |  | 589260000 | <1B | NS | Post | Prior | Plan | 27/1/22 | 17/2/22 | 2/3/22 | 16/3/21 | 31/3/22 | 6/4/22 | 14/4/22 | Plan | 28/4/22 | 29/4/22 | 589260000 |  | 12/5/22 | 2022-05-26 | 2/6/22 | 2022-06-09
[10 empty] | Actual | [7 empty] | Actual
| Total Cost |  |  |  | 1535032074 |  |  |  |  | Plan | [7 empty] | Plan |  |  | 1535032074
[10 empty] | Actual | [7 empty] | Actual

## WORKS
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY: OFFICE OF CHIEF OF STAFF
BUDGET YEAR: 2022
CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | Budget Avail | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDA | PPA No-Objection | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | NOTIFICATION OF AWARD | Date Contract Signature | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
|  |  | 0 | 0 |  |  |  | Plan |  | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4wks | 48hrs | 0 |  | 4-6 wks | 2-4 wks
Actual
Construction of Security Building/Police Station/Police Posts
Construction of Area C Police Command at Surulere- payment of balance (Outstanding Liability) |  | 1 | 102,840,063.31 | <500M | NCB | BOQ | Post | Plan | Prior | 3/2/22 | 2022-02-16 | 3/3/22 | 16/3/22 | 4/4/22 | 13/4/22 | 26/4/22 | 28/4/22 | 102,840,063.31 |  | 13/7/20 | 2021-05-27 | 2/6/21 | 2021-06-09
Actual
Construction of Odo-Noforija Police station (Outstanding Liability) |  | 1 | 4,933,168.99 | <10M | NCB | BOQ | Post | Plan | Prior | 6/01/22 | 2022-01-27 | 2022-02-10 | 24-2-22 | 9/3/21 | 24/3/22 | 6/4/22 | 8/4/22 | 4,933168.99 |  | 22/4/21 | 2021-05-04 | 18/5/21 | 2021-05-25
Actual
Construction Isee Police Station (87,588,248.79)- 15% Balance -( 13,138,237.32), 5% Retention - (4, 379,412.44), Additional Funds- ( 11,469,270.87) | OCOS/WKS/NCB-ST/002/20 | 1 | 17,517,649.76 | <50M | NCB | BOQ | Post | Plan | Prior | 6/01/22 | 2022-01-27 | 2022-02-10 | 24-2-22 | 9/3/21 | 24/3/22 | 6/4/22 | 8/4/22 | 17,517,649.76 |  | 22/4/21 | 2021-05-04 | 18/5/21 | 2021-05-25
Actual
Construction of State Security Services Office, Alimosho Local Government Area-N155,834,133.78. 40% Balance -N62,333,653.51 | OCOS/WKS/NCB-ST/003/20 | 1 | N62,333,653.51 | <50M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 62,333,653.51 |  |  | 2021-05-04 | 18/5/21 | 2021-05-25
[8 empty] | Actual | [6 empty] | 7/1/2021
Construction of State Security Services, Ikeja Local Government- | OCOS/W/NCB/001/22 | 1 | 155834133.78 | <500M | NCB | BOQ | Post | Plan | Prior | 6/01/22 | 2022-01-27 | 2022-02-10 | 24-2-22 | 9/3/21 | 24/3/22 | 6/4/22 | 8/4/22 | 155834133.78 |  | 19/4/22 | 2022-05-04 | 18/5/22 | 2022-05-25
Actual
Construction of Elepe Police Station, Igbogbo Bayeku Lcda | OCOS/W/NCB/002/22 | 1 | 386379133.11 | <500M | NCB | BOQ | Post | Plan | Prior | 6/01/22 | 2022-01-27 | 2022-02-10 | 24-2-22 | 9/3/21 | 24/3/22 | 6/4/22 | 8/4/22 | 386379133.11 |  | 19/4/22 | 2022-05-04 | 18/5/22 | 2022-05-25
Actual
REHABILITATION / EXPANSION /UPGRADING OF GOVERNMENT HOUSES AND VIP CHALETS AND LODGES
Rehabilitation/Renovation Works at Lagos Houses Ikeja and Marina | OCOS/W/NCB/003/22 | 1 | 179379412.44 | <500M | NS | BOQ | Post | Plan | Prior | 24/2/22 | 2022-03-09 | 22/3/22 | 6/4/22 | 19/4/22 | 3/5/22 | 17/5/22 | 18/5/22 | 179379412.44 |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Actual
Renovation Works at Government Guest Housesand VIP Chalets | OCOS/W/NCB/004/22 |  | 100000000 | <500M |  | BOQ | Post | Plan | Prior | 24/2/22 | 2022-03-09 | 22/3/22 | 6/4/22 | 19/4/22 | 3/5/22 | 17/5/22 | 18/5/22 | 100000000 |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Construction of Nigeria Army Forward Operation Base, Isawo ,Ikorodu and a Quarter Base at Epe to support the Operations of the Military in the Areas. |  | 1 | [5 empty] | Actual
Renovation Works at L-Wing Office Block Alausa Ikeja and Specch Writers Building |  | 1 | 30000000 | <50M |  |  |  | Plan |  | 24/2/22 | 2022-03-09 | 22/3/22 | 6/4/22 | 19/4/22 | 3/5/22 | 17/5/22 | 18/5/22 | 30000000 |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
| OCOS/W/NCB/005/22 | [6 empty] | Actual
Renovation/ Upgrade Works at Lagos State Fuel Dumps @ Alausa Ikeja. Marina and Police Command Ikeja. | OCOS/W/NCB/006/22 | 1 | 38748888.6 | <50M |  |  |  | Plan |  | 24/2/22 | 2022-03-09 | 22/3/22 | 6/4/22 | 19/4/22 | 3/5/22 | 17/5/22 | 18/5/22 | 38748888.6 |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Actual
|  | 1 | [5 empty] | Plan |  | 6/01/22 | 2022-01-27 | 2022-02-10 | 24-2-22 | 9/3/21 | 24/3/22 | 6/4/22 | 8/4/22 |  |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Actual
Construction of Security Building/Police Station/Police Posts
Construction of 20 Prototype Offices for State Security Service across the 20 Local Government Areas of Lagos State |  | 1 | [5 empty] | Plan |  | 6/01/22 | 2022-01-27 | 2022-02-10 | 24-2-22 | 9/3/21 | 24/3/22 | 6/4/22 | 8/4/22 |  |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Actual
Upgrade of Lekki Police Station,- 388,073,469.35 |  | 1 | [5 empty] | Plan |  | 6/01/22 | 2022-01-27 | 2022-02-10 | 24-2-22 | 9/3/21 | 24/3/22 | 6/4/22 | 8/4/22 |  |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Actual
General Rehabilitation of Mopol 49 Squardron - 144,588,442.60 |  | 1 | [5 empty] | Plan |  | 6/01/22 | 2022-01-27 | 2022-02-10 | 24-2-22 | 9/3/21 | 24/3/22 | 6/4/22 | 8/4/22 |  |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Actual
Construction of Modern Office Facility for Area N, Police Command | [7 empty] | Plan |  | 24/2/22 | 2022-03-09 | 22/3/22 | 6/4/22 | 19/4/22 | 3/5/22 | 17/5/22 | 18/5/22 |  |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Actual
Construction of Police Station at Tamaro - Onisiwo Royal Island of Amuwo Odofin Local Government | [7 empty] | Plan |  | 24/2/22 | 2022-03-09 | 22/3/22 | 6/4/22 | 19/4/22 | 3/5/22 | 17/5/22 | 18/5/22 |  |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Construction of Nigeria Army Forward Operation Base, Isawo ,Ikorodu and a Quarter Base at Epe to support the Operations of the Military in the Areas. | [7 empty] | Actual
Construction of Police Station at Agunfoye Community Ikorodu | [7 empty] | Plan |  | 24/2/22 | 2022-03-09 | 22/3/22 | 6/4/22 | 19/4/22 | 3/5/22 | 17/5/22 | 18/5/22 |  |  | 2/6/22 | 2022-06-16 | 30/6/22 | 2022-07-07
Actual
Plan
Actual
Plan
Actual
Total Cost |  |  | 1077966104 |  |  |  |  | Plan | [9 empty] | 1,077.966.104.00
Actual

## TRAINING
PROCUREMENT PLAN FOR TRAINING
MINISTRY/ AGENCY:
BUDGET YEAR:
OVERSEAS TRAINING CALENDER
S/N | Department | Description of Training & Venue | Participants | Designation | Plan vs Actual | Duration | Tuition Fee | Transport Fare | Allowance/Estacode | Visa Fee | Total Cost
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
| PLAN TOTAL |  |  |  | Plan
| ACTUAL TOTAL |  |  |  | Actual

## WORKSHOP
PROCUREMENT PLAN FOR CONFERENCE/TRAINING/WORKSHOP
MINISTRY/ AGENCY:OFFICE OF CHIEF OF STAFF
BUDGET YEAR: 2022
S/N | Description of Workshop/Conference | Objective of Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | (Nigerian Institute for Training and Development)PERMANENT SECRETARY | The Conference will provide a forum for interractions and exchange of ideas between policymakers | 1 | 4 days | Plan | Abuja | 60000 | 82000 | 240000 | 382000
Actual
2 | Nigerian Institute Management Workshop for Staff on GL 15-17 | To enhance participants skills in policy analysis and development of effective managerial skills | 2 | 4 days | Plan | Abuja | 120000 | 130000 | 384000 | 634000
Actual
3 | Nigerian Institute Management Workshop for Staff on GL 13-14 | To enhance participants skills in policy analysis and development of effective managerial skills | 4 | 4 days | Plan | Abuja | 240000 | 256000 | 576000 | 1072000
Actual
4 | Nigerian Institute Management Workshop for Staff on GL 10-12 | To enhance participants skills in policy analysis and development of effective managerial skills | 3 | 4 days | Plan | Abuja | 180000 | 183000 | 289000 | 652000
Actual
5 | Nigerian Institute for Training and Development for Staff on GL 15-17 | To address and profer solutions to issues of training and development in Nigeria. | 1 | 4 days | Plan | Abuja | 60000 | 65000 | 192000 | 317000
Actual
6 | Nigerian Institute for Training and Development for Staff on GL 13-14 | To address and profer solutions to issues of training and development in Nigeria. | 3 | 4 days | Plan | Abuja | 180000 | 192000 | 432000 | 804000
Actual
7 | Nigerian Institute for Training and Development for Staff on GL 10-12 | To address and profer solutions to issues of training and development in Nigeria. | 2 | 4 days | Plan | Abuja | 120000 | 122000 | 193000 | 435000
Actual
8 | Chartered Institute of Personnel Management Workshop for Staff on GL 15-17 | To upgrade participants managerial skills through management strategies and practices | 3 | 4 days | Plan | Abuja | 180000 | 195000 | 576000 | 951000
Actual
9 | Chartered Institute of Personnel Management Workshop for Staff on GL 13-14 | To upgrade participants managerial skills through management strategies and practices | 5 | 4 days | Plan | Abuja | 300000 | 320000 | 720000 | 1340000
Actual
10 | Chartered Institute of Personnel Management Workshop for Staff on GL GL 10-12 | To upgrade participants managerial skills through management strategies and practices | 4 | 4 days | Plan | Abuja | 240000 | 244000 | 386000 | 870000
Actual
11 | Nigerian Computer Society Workshop for Staff on GL 13-14 | To enhance participants skills in documents processing using computer technology | 2 | 4days | Plan | Abuja | 120000 | 128000 | 288000 | 536000
Actual
12 | Nigerian Computer Society Workshop for Staff on GL 10-12 | To enhance participants skills in documents processing using computer technology | 1 | 4days | Plan | Abuja | 60000 | 64000 | 144000 | 268000
Actual
13 | Nigerian Association of Technological Engineer Workshop for Staff on 13-14 | To develop & strenghten the competence of participants in the development of modern engineering concept | 1 | 4 days | Plan | Abuja | 60000 | 64000 | 144000 | 268000
Actual
14 | Council for the Regulation of Engineering in Nigeria Workshop for Staff on GL 10-12 | To develop & strenghten the competence of participants in the development of modern engineering concept | 1 | 4 days | Plan | Abuja | 60000 | 59500 | 98000 | 217500
Actual
15 | Nigerian Institute of Builders Workshop for Staff on GL 15-17 | To enhance theskills of participants in the management of developmental projects towards updating knowledge in the modern building technology | 1 | 4 days | Plan | Abuja | 60000 | 64000 | 144000 | 268000
Actual
16 | Nigerian Institute of Builders Workshop for Staff on GL 10-12 | To enhance theskills of participants in the management of developmental projects towards updating knowledge in the modern building technology | 1 | 4 days | Plan | Abuja | 60000 | 59500 | 98000 | 217500
Actual
17 | Nigerian Statistical Association Workshop for Staff on GL 13-14 | To enhance participants knowledge and skill in the use of tools and techniues for policy analysis | 1 | 4 days | Plan | Abuja | 60000 | 64000 | 144000 | 268000
Actual
18 | Nigerian Statistical Association Workshop for Staff on 10 -12 | To enhance participants knowledge and skill in the use of tools and techniues for policy analysis | 2 | 4 days | Plan | Abuja | 120000 | 119000 | 196000 | 435000
Actual
19 | Nigerian Environmental Society Workshop for Staff on GL 13-14 | To update the knowledge of participants in the challenges of environmental issues | 1 | 4 days | Plan | Abuja | 60000 | 64000 | 144000 | 268000
Actual
20 | Institute of Chartered Accountant of Nigerian Workshop for Staff on GL 13-14 | To improve the knowledge of participants in the elements of good governance with emphasis of transparency and transparency | 2 | 4 days | Plan | Abuja | 170000 | 128000 | 288000 | 586000
Actual
21 | Institute of Chartered Accountant of Nigerian Workshop for Staff on GL 10-12 | To improve the knowledge of participants in the elements of good governance with emphasis of transparency and transparency | 4 | 4 days | Plan | Abuja | 340000 | 238000 | 392000 | 970000
Actual
22 | Association of National Accountant of Nigeria Workshop for Staff on GL 15-17 | To enhance the skilsl of participants in efficient management of financial reseources | 2 | 4 days | Plan | Abuja | 120000 | 130000 | 384000 | 634000
Actual
23 | Asociation of National Accountant of Nigeria Workshop for Staff on GL 13-14 | To enhance the skilsl of participants in efficient management of financial reseources | 6 | 4 days | Plan | Abuja | 360000 | 384000 | 864000 | 1608000
Actual
24 | Asociation of National Accountant of Nigeria Workshop for Staff on GL 10-12 | To enhance the skilsl of participants in efficient management of financial reseources | 8 | 4 days | Plan | Abuja | 480000 | 488000 | 772000 | 1740000
Actual
25 | Mandatory Proficiency Programme in Chartered Institute of Purchasing Supply & Management of Nigeria(CIPSMN) for Staff on GL. 13-14 | To facilitate the exchange of knowledge in modern purchasing and procurement in Public Service | 2 | 5days | Plan | Abuja | 130000 | 128000 | 288000 | 546000
Actual
26 | Mandatory Proficiency Programme in Chartered Institute of Purchasing Supply & Management of Nigeria(CIPSMN) for Staff on GL. 12 | To facilitate the exchange of knowledge in modern Purchasing and Procurement in Public Service | 2 | 5days | Plan | Abuja | 65000 | 64000 | 122500 | 251500
Actual
27 | Institute of Public Analyst of Nigerian GL 10 -12 | To broaden and improve the managerial knowledge and attitude of participants towards an effective project management in Nigeria | 1 | 4days | Plan | Abuja | 60000 | 59500 | 98000 | 217500
Actual
28 | Economic Summit for Staff on GL. (10-12) | To sensitise participants to the uninspiring performance of Nigeria economy and reach a consensus on way forward | 2 | 4days | Plan | Abuja | 120000 | 122000 | 193000 | 435000
Actual
29 | Nigeria Hotel and Catering Institute(NHCI) for Staff on GL. 13-14 | To sensitise participants to the need for quality and excellent products and service delivery in order to meet the challenges of modern day hospitality industry | 4 | 4days | Plan | Abuja | 240000 | 256000 | 576000 | 1072000
Actual
30 | Nigeria Hotel and Catering Institute(NHCI) for Staff on GL. 10-12 | To sensitise participants to the need for quality and excellent products and service delivery in order to meet the challenges of modern day hospitality industry | 2 | 4days | Plan | Abuja | 300000 | 122000 | 193000 | 615000
Actual
31 | Coaching Mentoring & Interpersonal Relationshipfor Staff on GL 15-17 | Participants will be exposed to fundamental of coaching, mentoring and impact of interpersonal skills for organisational growth | 23 | 4days | Plan | Sango Otta | 1380000 | 350000 | 3406000 | 5136000
Actual
32 | Performance Appraisal for Optimal Productivity in Public Sectorfor Staff on GL 13-14 | It is to provide participants wwith basic toolsin performance appraisal analysis with emphasis on performance of individual and orgarnisation effectiveness | 88 | 4days | Plan | Ibadan | 5280000 | 1056000 | 8624000 | 14960000
Actual
33 | Improving Interpersional Effectiveness and Organisational Valuesmfor Staff on GL. 10-12 | It seek to improve interpersonal effectiveness and development strategies for improving organisation performance, reward efficient and effective service delivery | 80 | 4days | Plan | Ikeja | 4800000 | 120000 | 200000 | 5120000
Actual
34 | Managing Change for Excellent Performancefor Staff on GL. 7-9 | It seek to condition the participants attitude to the change process for optimal performance | 127 | 4days | Plan | Ikeja | 7620000 | 127000 | 190500 | 7937500
Actual
35 | Refresher Course for Drivers for Effective Motor Driviing for Staff on GL. 7 & 8 | The participants will refresh their skills and attititudes to reduce accidents on the road to the barest minimum | 69 | 4days | Plan | Oshodi | 4140000 | 69000 | 103500 | 4312500
Actual
36 | Defensive Driviing Techniues for Drivers for Staff on GL. 3-6 . | To expose participants to different tactics in driving under unusual circumstances | 52 | 4days | Plan | Ikeja | 3120000 | 36400 | 52000 | 3208400
Actual
37 | Attitudinal Change for Effective Service Delivery for Staff on GL 01-06 | To be able to develop set of positive attitude towards an effective service delivery | 116 | 4days | Plan | Ikeja | 6960000 | 81200 | 116000 | 7157200
Actual
38 | Middle Level Retreatfor Staff on GL07-12 | The participants would be able to lead a more effective and productive workgroup as well as assertive communication skills. | 138 | 3days | Plan | Lagos | 4140000 | 832000 | 5673392.5 | 10645392.5
Actual
39 | Senior Management Reatreat for Staff on GL13-17 | It is espected that the participants will confidently use ne skills in the workplace and have c clear plan of action and also be able to create a nurturing and productive environment in the workplace. | 107 | 3days | Plan | Lagos | 4280000 | 881000 | 6947707.5 | 12108707.5
Actual
| PLAN TOTAL |  |  |  | Plan |  |  |  |  | 30,00,000.00
| ACTUAL TOTAL |  |  |  | Actual
| Committee of Wives of Lagos State Officials on GL13-17 | It is espected that the participants will confidently use ne skills in the workplace and have c clear plan of action and also be able to create a nurturing and productive environment in the workplace. | 107 | 3days | Plan | Lagos |  |  | 6947707.5 | 350000000
Actual
| PLAN TOTAL |  |  |  | Plan
| ACTUAL TOTAL |  |  |  | Actual
| Sporsoring Members of Staff , Motorbikes, Spy Police, SA'S SSA's, Pas to Mr. Governor and PSAs to Relevant Workshops, Trainings and Retreat. Expenses incurred on TrainningAllowance for the Attendance of Officers to CIPM Conferences in Abuja= N15,670,000. Expenses incurred on TrainningAllowance for the Attendance of Officers to ICAN Conferences in Abuja= N10,250,000. Expenses incurred on TrainningAllowance for the Attendance of Officers to NES Conferences in Abuja= N1,800,000. Expenses incurred on TrainningAllowance for the Attendance of Officers to NITAD Conferences in Abuja= N2,280,000. | It is espected that the participants will confidently use the skills in the workplace and have clear plan of action and also be able to create a nurturing and productive environment in the workplace. |  |  | Plan |  |  |  |  | 30000000
Actual
| PLAN TOTAL |  |  |  | Plan |  |  |  |  | 410000000
| ACTUAL TOTAL |  |  |  | Actual