## goods
| MINISTRY/AGENCY: AGENCY FOR MASS EDUCATION |  |  |  | (PROCUREMENT PLAN FOR GOODS)
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Vocational trainig Furniture for Staffs and Trainees | AME/G/NS/001/22 | 1 | Various | 12000000 | <50M | NS | POST | PRIOR | Plan | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-30 | 6-Apr.-2022 | 2022-04-13 | 2022-04-27 | 2022-04-29 |  | 2022-05-06 | 2022-05-13 | 2022-05-27
Actual
2 | Procurement of vocational trainig materials and equipments | AME/G/NS/002/22 | 1 | Various | 24000000 | <50M | NS | POST | PRIOR | Plan | 2022-02-03 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-19 |  | 2022-03-26 | 2022-04-02 | 2022-04-09
Actual
3 | Procurement of Stationeries Materials for Departments/Units | AME/G/NS/003/22 | 1 | Various | 1200000 | <10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | NA | 2022-03-31 |  | 2022-04-07 | 2022-04-14 | 2022-04-21
Actual
| Procurement of Tyres, Tubes Batteries etc. | AME/G/NS/004/22 | 1 | Various | 180000 | <10M | NS | PRE | POST | Plan | NA | NA | NA | NA | NA | NA | NA | 2022-04-02 |  | 2022-04-09 | 2022-04-16 | 2022-04-23
Actual
4 | Procurement of uniforms for Drivers ,Secruities nd Cleaners | AME/G/NS/004/22 | 1 | Various | 55000 | <10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | NA | 2022-04-21 |  | 2022-04-28 | 2022-05-05 | 2022-05-12
Actual
5 | Procurement of Literacy materials | AME/G/NS/005/22 | 1 | Various | 1100000 | <10M | NS | POST | POST | Plan | NA | NA | NA | NA | NA | NA | NA | 2022-04-08 |  | 2022-04-15 | 2022-04-22 | 2022-04-29
Actual
6 | Procurement of Consumable for Maintenance of Office Building , Tonners / Computer Accessories and Operational Expenses forThree Units (MANAGEMENT INFORMATION SYSTEM) | AME/G/NS/006/22 | 1 | Various | 4675000 | <10M | NS | POST | POST | Plan | [8 empty] | NA | 2022-05-04 | 2022-05-11 | 2022-05-18 | bar: 2022-02-03 to 2022-03-19
Actual
7 | Procurement of Equipment / Repair of Vocational Equipment | AME/G/NS/007/22 | 1 | Various | 1049760 | <10M | NS | POST | POST | Plan | [9 empty] | 2022-04-29 | 2022-05-06 | 2022-05-13 | bar: 2022-02-03 to 2022-03-19
Actual
8 | Procurement of sharp Photocopier MX-M264N | AME/G/NS/008/22 | 1 | Various | 500000 | <10M | NS | POST | POST | Plan | [9 empty] | 2022-04-07 | 2022-04-14 | 2022-04-21 | bar: 2022-02-03 to 2022-03-19
Actual
9 | Procurement of printing materials for VTC certificates, banners,handbills and signboards | AME/G/NS/009/22 | 1 | LS | 5500000 | <10M | NS | POST | POST | Plan | [9 empty] | 2022-04-07 | 2022-04-14 | 2022-04-21 | bar: 2022-02-03 to 2022-03-09; 2022-03-19
Actual
10 | Procurement of Learning Materials for Literacy Centres | AME/G/NS/010/22 | 1 | LS | 30000000 | <50M | NS | PRIOR | PRIOR | Plan | [9 empty] | 2022-04-07 | 2022-04-14 | 2022-04-21 | bar: 2022-02-03 to 2022-03-19
Actual
11 | Procurement of gift items for Graduants and Celebration | AME/G/NS/011/22 | 1 | LS | 7700000 | <10M | NS | POST | POST | Plan | [9 empty] | 2022-04-07 | 2022-04-14 | 2022-04-21 | bar: 2022-02-03 to 2022-03-19
Actual
12 | Procurement of Materials for VTCs practical | AME/G/NS/012/22 | 1 | LS | 1500000 | <10M | NS | POST | POST | Plan | [9 empty] | 2022-04-07 | 2022-04-14 | 2022-04-21 | bar: 2022-02-03 to 2022-03-19
Actual
13 | Procurement of M/V Fuel (Running Cost) | AME/G/NS/013/22 | 1 | LS | 2388000 | <10M | NS | POST | POST | Plan | [9 empty] | 2022-04-07 | 2022-04-14 | 2022-04-21 | bar: 2022-02-03 to 2022-03-19
Actual

## NON.CONS
| MINISTRY/ AGENCY: AGENCY FOR MASS EDUCATION YEAR 2022 (PROCUREMENT PLAN FOR NON-CONSULTANCY) | [15 empty] | BUDGET YEAR: 2022
| Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Graduation Ceremony for Vocational Trainees | AME/S-NC/NS/001/22 | 1 |  | 13500000 | <50M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-31 | 2022-04-05 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-08
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
2 | Continuing Education centres, service of demand notice etc. | AME/S-NC/NS/002/22 | 1 | Various | 30000000 | <50M | NS | Plan | POST | POST | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | Plan | 2022-03-20 | 2022-02-25 |  | 2022-03-03 | 2022-03-10 | 2022-03-17 | 2022-03-24
[8 empty] | Actual | [9 empty] | Actual
3 | Sensitization and mobilization of campaign in all the Local Government Areass | AME/S-NC/NS/003/22 | 1 | Various | 7166500 | <10M | NS | Plan | POST | POST | 2022-02-02 | 2022-02-09 | 2022-02-16 | 2022-02-23 | 2022-03-02 | 2022-03-10 | 2022-03-17 | Plan | 2022-03-31 | 2022-04-05 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-08
[8 empty] | Actual | [9 empty] | Actual
4 | Monitoring and Evaluation | AME/S-NC/NS/004/22 | 1 |  | 2200000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-31 | 2022-04-05 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-08 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
5 | Maintenance of Office Building | AME/S-NC/NS/005/22 | 1 |  | 360000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-05-25 | 2022-05-26 |  | 2022-06-15 | 2022-06-28 | 2022-07-13 | 2022-07-27 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
6 | Servicing of utility vehicles | AME/S-NC/NS/006/22 | 1 |  | 180000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-04-06 | 2022-04-08 |  | 2022-04-22 | 2022-05-13 | 2022-05-27 | 2022-06-03 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
7 | International Literacy Day | AME/S-NC/NS/007/22 | 1 |  | 5000000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-15 | 2022-03-17 |  | 2022-04-14 | 2022-04-28 | 2022-06-09 | 2022-06-23 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
8 | Screening Exercise for Adult Learners | AME/S-NC/NS/008/22 | 1 |  | 2500000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-04-06 | 2022-04-08 |  | 2022-04-22 | 2022-05-13 | 2022-05-27 | 2022-06-03 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
9 | Annual Quiz Competition | AME/S-NC/NS/009/22 | 1 |  | 7000000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-15 | 2022-03-17 |  | 2022-04-14 | 2022-04-28 | 2022-06-09 | 2022-06-23 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
10 | Printing of Mass Literacy, VTC, Certificate, Banners, Handbills and Signboards. | AME/S-NC/NS/010/22 | 1 |  | 5500000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-05-25 | 2022-05-26 |  | 2022-06-15 | 2022-06-28 | 2022-07-13 | 2022-07-27 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
11 | Conducting Unified Assessment & Screening Exercise | AME/S-NC/NS/011/22 | 1 |  | 4050000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-31 | 2022-04-05 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-08 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
12 | Quarterly Mentoring of CDA/CDC members, evaluation and impact assessment of all CEC | AME/S-NC/NS/012/22 | 1 |  | 22000000 | <50M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-05-25 | 2022-05-26 |  | 2022-06-15 | 2022-06-28 | 2022-07-13 | 2022-07-27 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
13 | LSETF | AME/S-NC/NS/013/122 |  |  | 2000000 | <10M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-31 | 2022-04-05 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-08 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
14 | Statistical Report and Documentation (Literacy Survey Y2013 - 2021) | AME/S-NC/NS/015/122 |  |  | 15000000 | <50M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-31 | 2022-04-05 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-08 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
15 | 2022 International lIteracy Day Celebration (Rentage of Venue, Deocration and banners) | AME/S-NC/NS/015/122 |  |  | 550000 | <50M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-31 | 2022-04-05 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-08 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual
16 | Statistical Report and Documentation (Literacy Survey Y2013 - 2021) | AME/S-NC/NS/014/122 |  |  | 15000000 | <50M | NS | Plan | POST | POST | [7 empty] | Plan | 2022-03-31 | 2022-04-05 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-08 | bar: 2022-02-02 to 2022-03-17
|  |  |  | Various |  |  |  | Actual | [9 empty] | Actual

## tfgn, wsh and conf.
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: AGENCY FOR MASS EDUCATION
BUDGET YEAR: Y2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration (days) | Plan vs Actual | Venue | Tuition Fee N | Transport Fare N | Allowance N | Total Cost N
1 | Conference and Seminars | AME/S-WTC/0O1/22 | Capacity Building | 8 | 4 | Plan |  | 1688500
Actual
2 | Workshop and training ( | AME/S-WTC/0O2/22 | Capacity Building | 6 | 4 | Plan |  | 1155000
Actual
3 | Retreat for AME Staff | AME/S-WTC/003/22 | Capacity Building | 18 | 3 | Plan |  | 18700000
Actual
4 | 2022 JCC/NCE / professional seminars and meeting | AME/S-WTC/004/22 | Capacity Building | 4 | 4 | Plan |  | 418000
Actual
5 | HOS CUP | AME/S-WTC/005/22 | Capacity Building | 1 | 1 | Plan |  | 2200000
Actual
6 | Year 2022 Facilitator Conference | AME/S-WTC/006/22 | Capacity Building | 1 | 3 | Plan |  | 10000000
Actual

## NON. PROC ITEMS
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: AGENCY FOR MASS EDUCATION
BUDGET YEAR: Y2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/ Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Travel & Transport | AME/NP/NS/001/22 | 3500000 | Plan | 291667 | 291667 | 291667 | 291667 | 291667 | 291667 | 291667 | 291667 | 291667 | 291667 | 291667 | 291667
Actual
2 | General Utility Services | AME/NP/NS/002/22 | 420000 | Plan | MARCH: 105000; JUNE: 105000; SEPTEMBER: 105000; DECEMBER: 105000
Actual
3 | Miscellaneous(Unforeseen Circumstances) | AME/NP/NS/003/22 | 1776000 | Plan | MARCH: 444000; JUNE: 444000; SEPTEMBER: 444000; DECEMBER: 444000
Actual
4 | M/V Maintenance and Repair (Running cost) | AME/NP/NS/004/22 | 360000 | Plan | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
Actual
5 | Allowance for Monitoring and Evaluation Expenses | AME/NP/NS/005/22 | 2,200,000:00 | Plan | MARCH: 550000; JUNE: 550000; SEPTEMBER: 550000; DECEMBER: 550000
Actual
6 | Remuneration of external Auditor for (Y2021 - 2022) | AME/NP/NS/006/22 | 440000 | Plan | MARCH: 440000
Actual
7 | Program (Bond FM and Eko 107.5, Advocacy visit, Stakeholders HOD forum) | AME/NP/NS/007/22 | 33100000 | Plan | JANUARY: 8275000; APRIL: 8275000; JULY: 8275000; OCTOBER: 8275000
Actual
8 | Continue Education Centres (Servicing of Demand Notice, Bi Annual forum with CEC Stakeholders and Monitoring of CED | AME/NP/NS/008/22 | 30000000 | Plan | MARCH: 7500000; JUNE: 7500000; SEPTEMBER: 7500000; DECEMBER: 7500000
|  |  |  | Actual | JUNE: 15000000; OCTOBER: 15000000
9 | Publicity and Sensitization Campaign (Quarterly Stakeholders Enagement for Community Heads | AME/NP/NS/009/22 | 1100000 | Plan | MARCH: 691625; JUNE: 691625; SEPTEMBER: 691625; DECEMBER: 691625
|  |  |  | Actual | JUNE: 1100000
10 | Kick illiteracy out of Lagos: Allowance for 1000 facilitators @N15,000 x 12 Months | AME/NP/NS/010/22 | 180000000 | Plan | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
Actual
11 | Kick illiteracy out of Lagos: Allowance for 100 Instructors @N20,000 x 12 Months | AME/NP/NS/011/22 | 24000000 | Plan | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
Actual
12 | Kick illiteracy out of Lagos: Allowance for 100 External Coordinators @N20,000 x 12 Months | AME/NP/NS/012/22 | 3600000 | Plan | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
Actual
13 | Kick illiteracy out of Lagos: Allowance for 13 VTC Security Officers @N75,000 x 12 Months | AME/NP/NS/013/22 | 7800000 | Plan | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000
Actual
14 | Kick illiteracy out of Lagos: Allowance for 4 Security Officers at H/Q Alausa @N15,000 x 12 Months | AME/NP/NS/014/22 | 720000 | Plan | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
Actual
15 | Publication of MTSS documents / Monthly Data Collection | AME/NP/NS/015/22 | 550000 | Plan | NOVEMBER: 550000
Actual
Note on B14: ADEKUNLE AINA: DEFINE THE MISCELLANEOUS
Note on C10: ADEKUNLE AINA: Remove all NS or Procurement process from the package number

## CONSULT.
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: AGENCY FOR MASS EDUCATION
BUDGET YEAR: Y2022 PROCUREMENT PLAN FOR COJNSULTANCY SERVICES
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award |  | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Digitilazation of AME Activities | AME/S-C/CQS/001/22 | CQS | Lump sum | 8652530 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25/6/2022 | 29/6/2022 |  | 6/7/2022 | 13/7/2022 | 20/7/2022 | 27/7/2022 | 3/8/2022

## WORKS
PROCUREMENT PLAN FOR WORKS
MINISTRY: AME
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) | 1-4wks | 48 (hours) |  | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction and Renovation of Vocational Centers in (SURULERE, SABO LCDA, KASALI OLOWU, AGBOWA LCDA ADO, IKOSI EJIRIN LCDA, ORUGBO, AGEGE PHASE 2 AND IBEJU-LEKKI LCDA). | AME/W/NS/001/22 |  | 208142373.5 | <500M |  | BOQ | POST | Plan | PRIOR | 2022-04-02 | 2022-11-02 | 18/2/2022 | 25/2/2022 | 2022-04-03 | 2022-11-03 | 18/3/2022 | 2022-03-22 |  | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03
Actual
| Surulere LGA |  | 1 | 20000000 | <50M | NS
| Yaba (LCDA) Sabo |  | 2 | 15000000 | <50M | NS
| Epe (LGA) Kasali Oluwo |  | 3 | 30000000 | <50M | NS
| Agbowa (LCDA) Ado |  | 4 | 35000000 | <50M | NS
| Ikosi/Ejirin (LCDA) Orugbo |  | 5 | 45000000 |  | NS
| Agege (Phase e) |  | 6 | 25000000 | <50M | NS
| Ibeju-Lekki (LCDA) |  | 7 | 35142373.5 | <50M | NS