## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: MEPB
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | GENERAL UTILITY SERVICES |  | 3,380,867.00 | Plan
Actual
2 | SUNDRY EXPENSES |  | 21,068,044.77 | Plan
Actual
3 | COMMITTEE EXPENSES |  | 4781624.21 | Plan
Actual
4 | JANITORIAL SERVICES |  | 23,100,000.00 | Plan
Actual
5 | AWARDS & REWARDS |  | 1,489,602.56 | Plan
Actual
6 | SERVICE CHARTER EXPENSES |  | 1,489,602.56 | Plan
Actual
7 | RESEARCH & DEVELOPMENT |  | 33,327,651.00 | Plan
Actual
8 | SURVEY EXPENSES |  | 148,199,953.00 | Plan
Actual
9 | PERFORMANCE EVALUATION EXPENSES |  | 33,817,291.00 | Plan
Actual
6 | MULTILATERAL AGENCIES |  | 10463000 | Plan
Actual
7 | GRANT COORDINATING UNIT/ MGT OFFICE RUNNING COST |  | 30000000 | Plan
Actual
8 | OFFICE OF SPECIAL ADVISER |  | 10000000 | Plan
Actual
9 | SENIOR SPECIAL ASSISTANT EXPENSES |  | 5000000 | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: MEPB
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | WORKSHOP&TRAINING EXPENSES | MANDATORY PROFESSIONAL EDUCATION |  |  | Plan |  |  |  |  | 17220452
Actual
2 | CONFERENCE & SEMINARS | CHARTERED INSTITUTE PROGRAMME FOR CERTIFIED SECRETARIES |  |  | Plan |  |  |  |  | 56886780
Actual
3 | CAPACITY BUILDING EXPENSES | INDUCTION COURSE FOR EMPLOYED OFFICERS |  |  | Plan |  |  |  |  | 11468628
Actual
4 | Effective Budget Planning system and its impact on procurement implementation in ministries, department and agencies (MDAs) | C IPSMN: Effective manpower development of staff | 3 | 3 Days | Plan |  |  |  |  | 1056000
Actual
5 | All Mandatory/ Professional Training Programmes for year 2022. |  |  |  | Plan
[5 empty] | Actual |  |  |  |  | 86631860
6 |  |  |  |  | Plan
Actual
7 |  |  |  |  | Plan
Actual
8 |  |  |  |  | Plan
Actual
9 |  |  |  |  | Plan
Actual
10 |  |  |  |  | Plan
Actual
11 |  |  |  |  | Plan
Actual
12 |  |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON CONSULTING SERVICES
MINISTRY/ AGENCY: MEPB
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
TRAVEL & TRANSPORT - LOCAL | MEPB/NCS/NS/22/01 |  |  | 6053617 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
SPECIAL DUTIES EXPENSES |  |  |  | 29506908.88 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
PUBLICITY |  |  |  | 2071429.6 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
SERVICE CHARTER EXPENSES |  |  |  | 1380952.92 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
SERVICING OF MEETING |  |  |  | 3050000 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
TPRM |  |  |  | 2990000 |  |  | Plan | [8 empty] | 2021-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2021-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2021-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2022-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: MEPB
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | MANAGEMENT RETREAT | MEPB/CONS/QCBS/001/2022 | QCBS |  | 24049459.2 | Prior Review | Plan | 17/02/2022 | 2/03/2022 | 9/03/2022 | 6/04/2022 | 20/04/2022 | 4/5/2022 | 15/6/2022 | 29/6/2022 | 13/07/2022 | 20/07/2022 | 3/08/2022 | 17/08/2022 |  |  |  | 14/9/2022 | 28/9/2022 | 27/10/2022 | 9/11/2022 | 23/11/2022
Actual
2 | CAPACITY BUILDING EXPENSES | MEPB/CONS/QCBS/002/2022 | QCBS |  | 11468628 | Prior Review | Plan | 18/02/2022 | 3/03/2022 | 10/03/2022 | 7/04/2022 | 21/04/2022 | 5/5/2022 | 16/6/2022 | 30/6/2022 | 14/07/2022 | 21/07/2022 | 4/08/2022 | 18/08/2022 |  |  |  | 15/9/2022 | 29/9/2022 | 27/10/2022 | 10/11/2022 | 24/11/2022
Actual
3 | PREPARATION/REVIEW OF ANNUAL BUDGET | MEPB/CONS/QCBS/003/2022 | QCBS |  | 109179228 | Prior Review | Plan | 19/02/2022 | 4/03/2022 | 11/03/2022 | 08/04/2022 | 22/04/2022 | 6/5/2022 | 17/6/2022 | 1/7/2022 | 15/07/2022 | 22/07/2022 | 5/08/2022 | 19/08/2022 |  |  |  | 16/9/2022 | 30/9/2022 | 28/10/2022 | 11/11/2022 | 25/11/2022
Actual
4 | SUSTAINABLE DEVELOPMENT GOALS EXPENSES | MEPB/CONS/QCBS/004/2022 | QCBS |  | 1500000 | Post Review | Plan | 20/02/2022 | 5/03/2022 | 12/03/2022 | 09/04/2022 | 23/04/2022 | 7/5/2022 | 18/6/2022 | 2/7/2022 | 16/07/2022 | 23/07/2022 | 6/08/2022 | 20/08/2022 |  |  |  | 17/9/2022 | 1/10/2022 | 29/10/2022 | 12/11/2022 | 26/11/2022
Actual
5 | LAGOS STATE ECONOMIC INTELLIGENCE UNIT | MEPB/CONS/QCBS/005/2022 | QCBS |  | 54776559 | Prior Review | Plan | 21/02/2022 | 6/03/2022 | 13/03/2022 | 10/04/2022 | 26/04/2022 | 10/5/2022 | 21/6/2022 | 5/7/2022 | 19/07/2022 | 26/07/2022 | 9/08/2022 | 23/08/2022 |  |  |  | 20/9/2022 | 2/10/2022 | 1/11/2022 | 15/11/2022 | 29/11/2022
Actual
6 | ECONOMIC PLANNING PROGRAMMES | MEPB/CONS/QCBS/006/2022 | QCBS |  | 87495142 | Prior Review | Plan | 2022-02-24 | 2022-03-09 | 16/03/2022 | 13/04/2022 | 27/04/2022 | 2022-11-05 | 22/06/2022 | 2022-06-07 | 20/07/2022 | 27/07/2022 | 2022-10-08 | 24/08/2022 |  |  |  | 21/09/2022 | 2022-06-10 | 2022-02-11 | 16/11/2022 | 30/11/2022
Actual
7 | SURVEY EXPENSES | MEPB/CONS/QCBS/007/2022 | QCBS |  | 148199953 | Prior Review | Plan | 2022-02-25 | 2022-10-03 | 17/03/2022 | 14/04/2022 | 28/04/2022 | 2022-12-05 | 23/06/2022 | 2022-07-07 | 21/07/2022 | 28/07/2022 | 2022-11-08 | 25/08/2022 |  |  |  | 22/09/2022 | 2022-06-10 | 2022-03-11 | 17/11/2022 | 2022-12-01
Actual
8 | LBS MASTER PLAN | MEPB/CONS/QCBS/008/2022 | QCBS |  | 19000000 | Prior Review | Plan | 2022-02-26 | 2022-11-03 | 18/03/2022 | 15/04/2022 | 29/04/2022 | 13/05/2022 | 24/06/2022 | 2022-08-07 | 22/07/2022 | 29/07/2022 | 2022-12-08 | 26/08/2022 |  |  |  | 23/09/2022 | 2022-07-10 | 2022-04-11 | 18/11/2022 | 2022-02-12
Actual
9 | PERFORMANCE EVALUATION EXPENSES | MEPB/CONS/QCBS/009/2022 | QCBS |  | 33817291 | Prior Review | Plan | 2022-02-26 | 2022-12-03 | 19/03/2022 | 2022-04-16 | 30/04/2022 | 14/05/2022 | 25/06/2022 | 2022-09-07 | 23/07/2022 | 30/07/2022 | 13/08/2022 | 27/08/2022 |  |  |  | 24/09/2022 | 2022-08-10 | 2022-05-11 | 19/11/2022 | 2022-03-12
Actual
10 | MONITORING AND EVALUATION EXPENSES | MEPB/CONS/QCBS/010/2022 | QCBS |  | 94892937 | Prior Review | Plan | 2022-01-03 | 13/03/2022 | 19/03/2022 | 2022-04-17 | 2022-05-04 | 17/05/2022 | 28/06/2022 | 2022-10-07 | 24/07/2022 | 30/07/2022 | 16/08/2022 | 30/08/2022 |  |  |  | 27/09/2022 | 2022-09-10 | 2022-08-11 | 22/11/2022
Actual
11 | MULTILATERAL AGENCIES | MEPB/CONS/QCBS/010/2022 | QCBS |  | 10463000 | Prior Review | Plan | 2022-02-03 | 2022-01-04 | 23/03/2022 | 2022-04-19 | 2022-05-04 | 18/05/2022 | 29/06/2022 | 13/07/2022 | 27/07/2022 | 2022-03-08 | 17/08/2022 | 31/08/2022 |  |  |  | 28/09/2022 | 2022-12-10 | 2022-09-11 | 23/11/2022 | 2022-07-12
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: MEPB
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | STATIONERY | MEPB/GDS/01/2022 |  |  | 6719401 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-02-24 | 16/3/2022 | 2022-03-23 | 2022-05-04 | 2022-05-11 | 2022-05-18 |  |  |  |  | 2022-06-08 | 2022-06-16
Actual
2 | MANAGEMENT INFORMATION SYSTEM | MEPB/GDS/02/2022 |  |  | 18680842 |  | NATIONAL SHOPPING |  | PRIOR | Plan | 2022-02-25 | 17/3/2022 | 2022-03-24 | 2022-05-05 | 2022-05-12 | 2022-05-19 |  |  |  |  | 2022-06-09 | 2022-06-16
Actual
3 | UNIFORM&PROTECTIVE WEARS | MEPB/GDS/03/2022 |  |  | 1091938.5 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-02-26 | 18/3/2022 | 2022-03-25 | 2022-05-06 | 2022-05-13 | 2022-05-20 |  |  |  |  | 2022-06-10 | 2022-06-17
Actual
4 | PROCUREMENT OF DIESEL | MEPB/GDS/04/2022 |  |  | 24218000 |  | NATIONAL SHOPPING |  | PRIOR | Plan | 2022-02-26 | 2022-03-19 | 2022-03-26 | 2022-05-07 | 2022-05-14 | 2022-05-21 |  |  |  |  | 2022-06-11 | 2022-06-18
Actual
5 | CLEANING MATERIALS | MEPB/GDS/05/2022 |  |  | 5117202 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-02-26 | 2022-03-22 | 2022-03-26 | 2022-05-10 | 2022-05-17 | 2022-05-21 | [5 empty] | 2022-06-21
Actual
6 | PROCUREMENT UNIT EXPENSES | MEPB/GDS/06/2022 |  |  | 4923606.02 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-02 | 23th-03-2022 | 2022-03-30 | 2022-05-11 | 2022-05-18 | 2022-05-25 | [5 empty] | 2022-06-22
Actual
6 | STORE UNIT EXPENSES | MEPB/GDS/06/2022 |  |  | 444998 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-02 | 23th-03-2022 | 2022-03-30 | 2022-05-11 | 2022-05-18 | 2022-05-25 | [5 empty] | 2022-06-22
Actual
7 | PLANNING UNIT EXPENSES | MEPB/GDS/07/2022 |  |  | 8565814 |  | NATIONAL SHOPPING |  | PRIOR | Plan | 2022-03-03 | 24th-03-2022 | 2022-03-31 | 2022-05-12 | 2022-05-19 | 2022-05-26 | [5 empty] | 2022-06-23
Actual
8 | PUBLICATION AND DOCUMENTATION | MEPB/GDS/08/2022 |  |  | 8127570 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-04 | 25th-03-2022 | 2022-01-04 | 2022-05-13 | 2022-05-20 | 2022-05-27 | [5 empty] | 2022-06-24
Actual
9 | PUBLIC RELATION EXPENSES | MEPB/GDS/09/2022 |  |  | 15589655 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-05 | 26th-03-2022 | 2022-04-02 | 2022-05-14 | 2022-05-21 | 2022-05-28 | [5 empty] | 2022-06-25
Actual
10 | AUDIT EXPENSES | MEPB/GDS/010/2022 |  |  | 4678121 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-08 | 29th-03-2022 | 2022-04-05 | 2022-05-15 | 2022-05-21 | 2022-05-28 | [5 empty] | 2022-06-28
Actual
11 | PREPARATION OF ANNUAL ESTIMATE | MEPB/GDS/011/2022 |  |  | 107169007 |  | NATIONAL SHOPPING | Pre-Qualification | PRIOR | Plan | 2022-03-09 | 30th-03-2022 | 2022-04-06 | 2022-05-18 | 2022-05-25 | 2022-06-01 | [5 empty] | 2022-06-29
Actual
12 | ICT UNIT EXPENSES | MEPB/GDS/012/2022 |  |  | 8622168 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-10 | 31st-Mar-2022 | 2022-04-07 | 2022-05-19 | 2022-05-26 | 2022-06-02 | [5 empty] | 2022-06-30
Actual
13 | BANKING OPERATION SERVICES | MEPB/GDS/013/2022 |  |  | 1715000 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-11 | 1st-April-2022 | 2022-04-08 | 2022-05-20 | 2022-05-27 | 2022-06-03 | [5 empty] | 2022-07-01
Actual
14 | REVENUE STAKEHOLDERS MEETING | MEPB/GDS/014/2022 |  |  | 2820378 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-12 | 2nd -Apr-2022 | 2022-04-09 | 2022-05-21 | 2022-05-28 | 2022-06-04 | [5 empty] | 2022-07-02
Actual
15 | SOCU EXPENSES | MEPB/GDS/015/2022 |  |  | 80915225 |  | NATIONAL SHOPPING |  | PRIOR | Plan | 2022-03-13 | 5th-April-2022 | 2022-04-12 | 2022-05-22 | 2022-05-29 | 2022-06-07 | [5 empty] | 2022-07-05
Actual
16 | LIBRARY SERVICES | MEPB/GDS/016/2022 |  |  | 1000000 |  | NATIONAL SHOPPING |  | POST | Plan | 2022-03-12 | 5th-April-2022 | 2022-04-12 | 2022-05-21 | 2022-05-28 | 2022-06-04 | [5 empty] | 2022-07-02
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: MEPB
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | MAINTENANCE OF OFFICE BUILDING | MEPB/W/NS/2022/1 |  | 1836000 |  | NS | Lump Sum or Bill of Quantity | POST | Plan | POST | NA | NA | NA | NA | NA | NA |  |  | 1836000
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual