## trg conf wsh (3)
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LASODA
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | MANDATORY CONTINOUS PROFESSIONAL EDUCATION:PERSONAL EFFECTIVENESS AND TIME MANAGEMENT | LASODA/S-WTC/SS/001/22 | Staff development and work efficiency enhancement | 2 | 2 Days | Plan | NITAD, PORT-HARCOURT | 50000 | 65000 | 146000 | 261000
Actual
2 | ALIGNING THE STRATEGIC PUBLIC PROCUREMENT AND SUPPLY CHAIN MGT PRACTICES WITH GOOD CORPORATE GOVT TOWARDS ATTAINMENT OF THE NEXT LEVEL AGENDA OF GOVT. | LASODA/S-WTC/SS/002/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | CIPSMN, Abuja | 60000 | 64000 | 109000 | 233500
Actual
3 | PROBLEM ANALYSIS, SOLVING AND DECISION MAKING | LASODA/S-WTC/SS/003/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | EAAN, Enugu | 65000 | 64000 | 109500 | 238000
Actual
4 | BUSINESS INTELLIGENCE AND ANALYTICS FOR HR PROFESSIONALS | LASODA/S-WTC/SS/004/22 | Staff development and work efficiency enhancement | 2 | 2 Days | Plan | CIPM, Abuja | 80000 | 61000 | 73500 | 214500
Actual
5 | Work Ethics and Organization Productivity | LASODA/S-WTC/SS/005/22 | Staff development and work efficiency enhancement | 2 | 3 Days | Plan | EAAN, Ogun St | 65000 | 12000 | 98000 | 175000
Actual
6 | Effective Service Delivery | LASODA/S-WTC/SS/006/22 | Staff development and work efficiency enhancement | 2 | 4 Days | Plan | NIPR, Ogun St | 65000 | 10000 | 90750 | 165750
Actual
7 | Financial Accounting and Reporting- A Strategy for Service Delivery for Accounts staff | LASODA/S-WTC/SS/007/22 | Staff development and work efficiency enhancement | 1 | 4 Days | Plan | ICAN, Ogun St | 65000 | 10000 | 90750 | 165750
Actual
8 | Financial Accounting and Reporting- A Strategy for Service Delivery for Accounts staff | LASODA/S-WTC/SS/008/22 | Staff development and work efficiency enhancement | 1 | 4 Days | Plan | ICAN, Ogun St | 65000 | 7500 | 60500 | 133000
Actual
9 | Cloud Management and Security: Principles and Best Practice course for ICT staff | LASODA/S-WTC/SS/009/22 | Staff development and work efficiency enhancement | 2 | 3 Days | Plan | NS&T.com, Ikeja | 110000 | 4000 | 1500 | 115500
Actual
10 | Audit Planning and Control: Best Practices | LASODA/S-WTC/SS/010/22 | Staff development and work efficiency enhancement | 1 | 5 Days | Plan | ICAN, Ikeja | 105990 | 5000 | 1500 | 112490
Actual

## trg conf wsh (2)
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LASODA
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | EMOTIONAL INTELLIGENCE AT THE WORKPLACE | LASODA/S/WTC/001/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | PORT-HARCOURT | 100000 | 110000 | 247800 | 457800
2 | EFFECTIVE COACHING AND MENTORING SKILL FOR SENIOR MANAGERS | LASODA/S/WTC/002/22 | Staff development and work efficiency enhancement | 4 | 3 Days | Plan | MODOTEL, ENUGU | 85000 | 110000 | 247800 | 442800
Actual
3 | TARGET SETTING PERFORMANCE MANAGEMENT | LASODA/S/WTC/003/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | PORT-HARCOURT | 100000 | 110000 | 247800 | 457800
4 | ACCOUNTS RECONCILIATION STRATEGIES AND MANAGEMENT OF SUSPENCE ACCOUNT | LASODA/S/WTC/004/22 | Staff development and work efficiency enhancement | 1 | 5 Days | Plan | ICAN, ENUGU | 85000 | 110000 | 247800 | 442800
Actual
5 | PROCUREMENT PLANNING FOR WORKS, GOODS AND SERVICES IN MDAS AND PRIVATE SECTOR | LASODA/S/WTC/005/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | CIPSMN, Abuja | 100000 | 110000 | 189000 | 399000
Actual
6 | CORPORATE SOCIAL RESPONSIBILITY AND COMMUNITY RELATIONS PROGRAMS FOR BRAND MANAGEMENT | LASODA/S/WTC/006/22 | Staff development and work efficiency enhancement | 1 | 1 Day | Plan | NIPR, Enugu | 175000 | 18000 | 120000 | 313000
Actual
7 | RESULT ORIENTED MANAGEMENT FOR ADMINISTRATORS | LASODA/S/WTC/007/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | EAAN IBADAN | 85000 | 18000 | 120400 | 222400
Actual
8 | FUNDAMENTAL PRINCIPLES OF FINANCIAL REPORTING AND ANALYSIS | LASODA/S/WTC/008/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | ICAN, Ogun St | 85000 | 18000 | 120400 | 222400
Actual
9 | COMPUTER TRAINING FOR BLIND | LASODA/S/WTC/009/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | V&S T, P/H | 200000 | 18000 | 110400 | 337400
Actual
10 | INTEGRATED PERSONNEL AND PAYROLL INFORMATION SYSTEM | LASODA/S/WTC/010/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | ICAN, Ogun St | 85000 | 18000 | 110400 | 222400
Actual
11 | EMPLOYMENT LAWS, REGULATION AND LEGAL PRACTICES | LASODA/S/WTC/011/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | CIPM, Abuja | 100000 | 18000 | 110400 | 237400
Actual
GL 07-12
12 | EMPLOYMENT LAWS, REGULATION AND LEGAL PRACTICES | LASODA/S/WTC/012/22 | Staff development and work efficiency enhancement | 2 | 3 Days | Plan | CIPM, Abuja | 100000 | 15000 | 82800 | 208550
Actual
13 | CORPORATE SOCIAL RESPONSIBILITY AND COMMUNITY RELATIONS PROGRAMS FOR BRAND MANAGEMENT | LASODA/S/WTC/013/22 | Staff development and work efficiency enhancement | 1 | 1 Day | Plan | NIPR, Enugu | 100000 | 15000 | 61950 | 174950
Actual
14 | PREPARATION, PRESENTATION AND ANALYSIS OF FINANCIAL STATEMENTS | LASODA/S/WTC/014/22 | Staff development and work efficiency enhancement | 2 | 3 Days | Plan | ICAN, Abeokuta | 85000 | 15000 | 89550 | 189550
Actual
15 | IMPROVING MANAGEMENT IN THE PUBLIC SERVICE | LASODA/S/WTC/015/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | BEZER HALL , Abeokuta | 85000 | 15000 | 89550 | 189550
Actual
16 | ELECTRONIC RECORDS MANAGEMENT | LASODA/S/WTC/016/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | BEZER HALL , Abeokuta | 85000 | 15000 | 89550 | 189550
Actual
17 | ETHICS & ATTITUDINAL CHANGE IN PUBLIC SERVICE | LASODA/S/WTC/017/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | BEZER HALL , Abeokuta | 85000 | 11250 | 59700 | 155950
Actual
18 | CONFERENCE OF PRACTITIONERS | LASODA/S/WTC/018/22 | Staff development and work efficiency enhancement | 1 | 1 Day | Plan | NIPR , ABUJA | 50000 | 110000 | 38100 | 198100
Actual
19 | AUDITING & INVESTIGATION | LASODA/S/WTC/019/22 | Staff development and work efficiency enhancement | 1 | 3 Days | Plan | OSBCC, IBADAN | 85000 | 11250 | 59700 | 155950
Actual
20 | ETHICS & ATTITUDINAL CHANGE IN PUBLIC SERVICE | LASODA/S/WTC/017/22 | Staff development and work efficiency enhancement | 3 | 3 Days | Plan | BEZER HALL , Abeokuta | 85000 | 11250 | 59700 | 155950
Actual
21 | FINANCIAL MANAGEMENT AND EXPENDITURE CONTROL | LASODA/S/WTC/018/22 | Staff development and work efficiency enhancement | 2 | 4 Days | Plan | ICAN, Ikeja | 85000 | 11250 | 59700 | 155950
Actual

## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LASODA
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Social Security Provision of Financial Grant to 500 PWDs @ 100,000.00 each | LASODA/NP/NS/001/22 | 50,000,000.00 | Plan | [12 empty] | 50000000
Actual
2 | Medical Intervention for PWDs | LASODA/NP/NS/002/22 | 8,000,000.00 | Plan | [12 empty] | 8000000
Actual
3 | Cash Support to 9 Associations, Homes, etc of PWDs Lagos Chapters. | LASODA/NP/NS/003/22 | 12140000 | Plan | [12 empty] | 12140000
Actual
4 | Monitoring, Evaluation & Orientation Unit Expenses | LASODA/NP/NS/004/22 | 800,000.00 | Plan | [12 empty] | 800000
Actual
5 | Committee Expenses | LASODA/NP/NS/005/22 | 1,000,000.00 | Plan | [12 empty] | 1000000
Actual
6 | Special Duties Expenses | LASODA/NP/NS/006/22 | 4000000 | Plan | [12 empty] | 4000000
Actual
7 | Publicity and Press coverage | LASODA/NP/NS/007/22 | 500,000.00 | Plan | [12 empty] | 500,000.00
Actual
8 | PWDs Enhancement Programme (Cash support to Associations) | LASODA/NP/NS/008/22 | 21,000,000,000 | Plan | [12 empty] | 21000000
Actual
9 | Local Travel & Transport: expenses to despatch mails, monitor team visits on PWDs related matters, & for GM/ Management staff. | LASODA/NP/NS/009/22 | 2,700,000 | Plan | [12 empty] | 2700000
Actual
10 | Allowances for front desk Sign Interpreters, NYSC staff, IT Students & Cleaner (Maintenance of Office building) | LASODA/NP/NS/010/22 | 920,000 | Plan | [12 empty] | 920000
Actual
11 | Renewal of Vehicle particulars (Maintenance of Office building) | LASODA/NP/NS/011/22 | 75,000.00 | Plan | [12 empty] | 75000
Actual
12 | General Utility Services: Telephone bills, CCTV Camera, Office Internet expenses | LASODA/NP/NS/012/22 | 3017500 | Plan | [12 empty] | 3017500
Actual
13 | Miscellaneous: Unforeseen injuries/ death, Staff hazard and purchase of Newspapers & Margazines expenses | LASODA/NP/NS/013/22 | 1,516,530.00 | Plan | [12 empty] | 1516630
Actual
14 | Fund for payment of External Auditor expenses | LASODA/NP/NS/014/22 | 870,000.00 | Plan | [12 empty] | 870000
Actual
15 | Internal Audit unit expenses: Quarterly auditing of Agency's staff | LASODA/NP/NS/015/22 | 100000 | Plan | [12 empty] | 100000
Actual
16 | Public Relation unit maintenance expenses | LASODA/NP/NS/016/22 | 150,000.00 | Plan | [12 empty] | 150000
Actual
17 | Enlightenment & Campaign: Sensitizing the public about LSSPL using various media | LASODA/NP/NS/017/22 | 800,000.00 | Plan | [12 empty] | 800000
Actual
18 | LIBRARY: Stock Journals, research books, etc and on PWDs issues | LASODA/NP/NS/018/22 | 300000 | Plan | [12 empty] | 300000
Actual
19 | Planning Research & Statistics Unit Expenses: fund for annual budget preparation and materials | LASODA/NP/NS/019/22 | 200000 | Plan | [12 empty] | 200000
Actual
20 | Procurement Unit expenses: PTB meetings servicing and materials | LASODA/NP/NS/020/22 | 150000 | Plan | [12 empty] | 150000
Actual
21 | Partnership & Linkages | LASODA/NP/NS/021/22 | 856899 | Plan | [12 empty] | 856899
Actual
22 | ICT Unit Expenses: maintenance of IT equipment and materials. | LASODA/NP/NS/022/22 | 150000 | Plan | [12 empty] | 150000
Actual
23 | Printing of Lagos State Special People Law | LASODA/NP/NS/023/22 | 100000 | Plan | [12 empty] | 100000
Actual
24 | SSA EXPENSES: Provision of fund for the SSA Expenses and other PWDs related issues. | LASODA/NP/NS/024/22 | 2500000 | Plan | [12 empty] | 2500000
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LASODA
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Short distance training for LASODA Staff between GL 14-17 | LASODA/S-WTC/SS/001/22 | Staff development and work efficiency enhancement | 8 |  | Plan |  |  |  |  | 640000
Actual
2 | Short distance training for LASODA Staff between GL 12-13 | LASODA/S-WTC/SS/002/22 | Staff development and work efficiency enhancement | 4 |  | Plan |  |  |  |  | 240000
Actual
3 | Short distance training for LASODA Staff between GL 08-10 | LASODA/S-WTC/SS/003/22 | Staff development and work efficiency enhancement | 9 |  | Plan |  |  |  |  | 150000
Actual
4 | Short distance training for LASODA Staff between GL 04-07 | LASODA/S-WTC/SS/004/22 | Staff development and work efficiency enhancement | 3 |  | Plan |  |  |  |  | 100000
Actual
5 | A&HR Dept payment of allowances for officers conference & seminar | LASODA/S-WTC/SS/005/22 | A&HR Dept payment of allowances for officers conference & seminar | 1 |  | Plan |  |  |  |  | 250000
Actual
6 | (Support Staff) payment of allowances for officers conference & seminar | LASODA/S-WTC/SS/006/22 | (Support Staff) payment of allowances for officers conference & seminar | 7 |  | Plan |  |  |  |  | 1514000
Actual
7 | Accounts Dept payment of allowances for officers conference & seminar | LASODA/S-WTC/SS/007/22 | Accounts Dept payment of allowances for officers conference & seminar | 1 |  | Plan |  |  |  |  | 180000
Actual
8 | Audit Dept payment of allowances for officers conference & seminar | LASODA/S-WTC/SS/008/22 | Audit Dept payment of allowances for officers conference & seminar | 1 |  | Plan |  |  |  |  | 106000
Actual
9 | P&S Dept payment of allowances for officers conference & seminar | LASODA/S-WTC/SS/009/22 | P&S Dept payment of allowances for officers conference & seminar | 1 |  | Plan |  |  |  |  | 150000
Actual
10 | Payment for attendance of COWLSO by female officers | LASODA/S-WTC/SS/010/22 | Payment for attendance of COWLSO by female officers | 10 |  | Plan |  |  |  |  | 800000
Actual
11 | Exchange Programme: International training on Social Inclusive programme | LASODA/S-WTC/SS/011/22 | Exchange Programme: International training on Social Inclusive programme | 1 |  | Plan |  |  |  |  | 1000000
Actual
12 | Capacity Building: Staff training on LASODA issues, and PWDs handling | LASODA/S-WTC/SS/012/22 | Capacity Building: Staff training on LASODA issues, and PWDs handling | All Staff |  | Plan |  |  |  |  | 335198.5
Actual

## non-cons
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/ AGENCY: LASODA
BUDGET YEAR: 2022
| Contract Description | BASIC DATA | [7 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
S/N |  | Package Number |  | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Celebration of International Days of women/ Mothers Living with Disabilities. | LASODA/S-NC-F/NS/001/22 |  |  |  | 7720000 | <10M | NS | Plan | POST | POST | 2022-03-04 | 2022-03-25 | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 | NA | Plan | NA | NA |  | 2022-06-10 | 2022-06-17 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
2 | Stakeholders Forum with Private Organizations and Corporate bodies, etc. | LASODA/S-NC/NS/002/22 |  |  | 2 | 4000000 | <10M | NS | Plan | POST | POST | 2022-02-24 | 2022-03-16 | 2022-03-23 | 2022-05-04 | 2022-05-11 | 2022-05-18 | NA | Plan | NA | NA |  | 2022-06-01 | 2022-06-08 | 2022-06-15
[9 empty] | Actual | [9 empty] | Actual
3 | Subscription: printing of LSSPL | LASODA/S-NC/NS/003/22 |  |  |  | 350000 | <10M | NS | Plan | POST | POST | 2022-02-25 | 2022-03-17 | 2022-03-24 | 2022-05-05 | 2022-05-12 | 2022-05-19 | NA | Plan | NA | NA |  | 2022-06-02 | 2022-06-09 | 2022-06-16
[9 empty] | Actual | [9 empty] | Actual
4 | Servicing of Meeting | LASODA/S-NC/NS/004/22 |  |  |  | 1000000 | <10M | NS | Plan | POST | POST | 2022-02-27 | 2022-03-19 | 2022-03-26 | 2022-05-07 | 2022-05-14 | 2022-05-21 | NA | Plan | NA | NA |  | 2022-06-04 | 2022-06-11 | 2022-06-18
[9 empty] | Actual | [9 empty] | Actual
5 | Social Development & Integration: organizing Interactive quiz between Regular & Special schools; meeting with Excos of Disabled Organizations, Head of Voluntary Organizations, Youth leaders of Community base Organization PWDs | LASODA/S-NC/NS/005/22 |  |  |  | 4800000 | <10M | NS | Plan | POST | POST | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-05-08 | 2022-05-15 | 2022-05-22 | NA | Plan | NA | NA |  | 2022-06-05 | 2022-06-12 | 2022-06-19
[9 empty] | Actual | [9 empty] | Actual
6 | Special Children Financing: Sensitization awareness capturing children 0-18 yrs of age, & projecting inclusive education & technology friendly compliance to Stakeholders, parents/ caregivers | LASODA/S-NC/NS/006/22 |  |  |  | 2500000 | <10M | NS |  | POST | POST | 2022-03-02 | 23th-03-2022 | 2022-03-30 | 2022-05-11 | 2022-05-18 | 2022-05-25 | NA | Plan | NA | NA |  | 2022-06-08 | 2022-06-15 | 2022-06-22
[9 empty] | Actual | [9 empty] | Actual
7 | Organizing Sign Language Workshop programme | LASODA/S-NC/NS/007/22 |  |  |  | 4000000 | <10M | NS | Plan | POST | POST | 2022-03-03 | 24th-03-2022 | 2022-03-31 | 2022-05-12 | 2022-05-19 | 2022-05-26 | NA | Plan | NA | NA |  | 2022-06-09 | 2022-06-16 | 2022-06-23
[9 empty] | Actual | [9 empty] | Actual
8 | Annual Celebration of International Days for Disabilities (IDD) on 3rd December. | LASODA/S-NC/NS/008/22 |  |  |  | 7000000 | <10M | NS | Plan |  |  | 2022-02-25 | 2022-03-17 | 2022-03-24 | 2022-05-05 | 2022-05-12 | 2022-05-19 | NA | Plan | NA | NA |  | 2022-06-02 | 2022-06-09 | 2021-06-16
[9 empty] | Actual | [9 empty] | Actual
9 | Publicity and Press coverage | LASODA/S-NC/NS/009/22 | LASODA/NP/NM/004/20 |  |  | 500000 | <10M | NS | Plan |  |  | 2022-02-27 | 2022-03-19 | 2022-03-26 | 2022-05-07 | 2022-05-14 | 2022-05-21 | NA | Plan | NA | NA |  | 2022-06-04 | 2022-06-11 | 2022-06-18
[9 empty] | Actual | [9 empty] | Actual
10 | Exhibition & Trade fairs | LASODA/S-NC/NS/010/22 |  |  |  | 3280000 | <10M | NS | Plan | POST | POST | 2022-01-28 | 2022-02-11 | 2022-02-25 | 2022-04-01 | 2022-04-15 | 2022-04-22 | NA | Plan | NA | NA |  | 2022-05-05 | 2022-05-12 | 2022-05-19
[9 empty] | Actual | [9 empty] | Actual
11 | Celebration of International White Cane for the Blind | LASODA/S-NC/NS/011/22 | LASODA/NP/NM/004/20 |  |  | 1000000 | <10M | NS | Plan | POST | POST | 2022-03-02 | 23th-03-2022 | 2022-03-30 | 2022-05-11 | 2022-05-18 | 2022-05-25 | NA | Plan | NA | NA |  | 2022-06-08 | 2022-06-15 | 2022-06-22
[9 empty] | Actual | [9 empty] | Actual
12 | Media Advocacy, Enlightenment &Campaign: Sensitization of the Public about the LSSPL using various Media Communication | LASODA/S-NC/NS/012/22 | LASODA/NP/NM/004/20 |  | 4 | 16000000 | <50M | NS | Plan | POST | POST | 2022-03-03 | 24th-03-2022 | 2022-03-31 | 2022-05-12 | 2022-05-19 | 2022-05-26 | NA | Plan | NA | NA |  | 2022-06-09 | 2022-06-16 | 2022-06-23
[9 empty] | Actual | [9 empty] | Actual
13 | Printing of Lagos State Special People Law | LASODA/S-NC/NS/012/22 | LASODA/NP/NM/004/20 |  |  | 350000 | <10M | NS | Plan | POST | POST | 2022-03-03 | 24th-03-2022 | 2022-03-31 | 2022-05-12 | 2022-05-19 | 2022-05-26 | NA | Plan | NA | NA |  | 2022-06-09 | 2022-06-16 | 2022-06-23
[9 empty] | Actual | [9 empty] | Actual
14 | ME&O DEPARTMENT: Sensitize the Public about LSSPL and incidental Expenses during monitoring of cases of discriminations in all 57 LG & LCDAs and compliance of LSSPL within the Lagos State Secretariat. | LASODA/S-NC/NS/013/22 | LASODA/NP/NM/004/20 |  |  | 800000 |  | NS | Plan | POST | POST | 2022-03-02 | 23th-03-2022 | 2022-03-30 | 2022-05-11 | 2022-05-18 | 2022-05-25 | NA | Plan | NA | NA |  | 2022-06-08 | 2022-06-15 | 2022-06-22
[9 empty] | Actual | [9 empty] | Actual
13 | Printing of Lagos State Special People Law | LASODA/S-NC/NS/012/22 | LASODA/NP/NM/004/20 |  |  | 100000 | <10M | NS | Plan | POST | POST | 2022-03-03 | 24th-03-2022 | 2022-03-31 | 2022-05-12 | 2022-05-19 | 2022-05-26 | NA | Plan | NA | NA |  | 2022-06-09 | 2022-06-16 | 2022-06-23
[9 empty] | Actual | [9 empty] | Actual
15 | Renewal of Vehicle particulars (Maintenance of Office building) | LASODA/S-NC/NS/014/22 | LASODA/NP/NM/004/20 |  | 4 | 75,000.00 |  | NS |  | POST | POST | 2022-03-03 | 24th-03-2022 | 2022-03-31 | 2022-05-12 | 2022-05-19 | 2022-05-26 | NA | Plan | NA | NA |  | 2022-06-09 | 2022-06-16 | 2022-06-23
[9 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LASODA
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPAV5:X5 | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Digitalization of LASODA with Training of Front Desk Officers | LASODA/S-C/QCBS/001/22 | QCBS |  | 32794260 | Prior | Plan | 20/04/2022 | 3/05/2022 | 17/05/2022 | 24/5/22 | 31/5/22 |  | 14/6/2022 | 28/6/2022 | 26/07/2022 | 9/08/2022 | 23/08/2022 | 30/8/22 | 6/10/22 | 13/10/22 |  | 14/10/22 |  | 28/10/22
Actual
2 | Wealth Creation for PWDs | LASODA/S-C/QCBS/002/22 | QCBS |  | 130000000 | Prior | Plan | 21/04/2022 | 4/05/2022 | 18/05/2022 | 25/5/22 | 1/6/22 |  | 15/3/2022 | 29/3/2022 | 27/4/2022 | 10/5/2022 | 24/5/2022 | 31/5/22 | 7/6/22 | 14/6/22 |  | 15/6/22 |  | 29/7/22
Actual
3 | INCLUSIVE SCHOOL: Conduction of Assessment and peculiarity needs of selected inclusive Pry,Junior & Senior Sec., Special Schools & Percellie School for the Blind across 3 Divisions in Lagos State. | LASODA/S-C/QCBS/003/22 | QCBS |  | 45750000 | Prior | Plan | 22/02/2022 | 5/03/2022 | 19/03/2022 | 26/3/22 | 3/4/22 |  | 16/5/2022 | 30/5/2022 | 28/6/2022 | 11/7/2022 | 25/7/2022 | 1/8/22 | 8/8/22 | 15/8/22 |  | 16/8/22 |  | 23/8/22
Actual
4 | Organizing Lagos State Disability Sport Festival | LASODA/S-C/QCBS/004/22 | QCBS |  | 25000000 | Prior | Plan | 23/02/2022 | 6/03/2022 | 20/03/2022 | 27/3/22 | 4/4/22 |  | 17/5/2022 | 1/6/2022 | 29/6/2022 | 12/7/2022 | 26/7/2022 | 1/8/22 | 8/8/22 | 15/8/22 |  | 16/8/22 |  | 23/8/22
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LASODA
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Equipment/Assistive Devices for PWDs in Lagos State. | LASODA/G/NS/001/22 |  |  | 39266000 | <50M | NS | PRE | Prior | Plan | 2022-02-24 | 9/2 22 | 2022-03-23 | 2022-05-04 | 2022-05-11 | 2022-05-18 |  |  |  | 2022-06-01 | 2022-06-08 | 2022-06-15
Actual
2 | LIBRARY: Procurement of Stock Journals, Research books, etc on PWDs Issues | LASODA/G/NS/002/22 |  |  | 50000 | <10M | NS | Post | Post | Plan | 2022-02-25 | NA | 2022-03-24 | 2022-05-05 | 2022-05-12 | 2022-05-19 |  |  |  | 2022-06-02 | 2022-06-09 | 2022-06-16
Actual
3 | Motor Vehicle Fuel Consumption:Procurement of Engine Oil; Gear Oil; Fuel; and vehicle accessories | LASODA/G-F/NS/003/22 |  |  | 3720000 | <10M | NS | Post | Post | Plan | 2022-02-26 | NA | 2022-03-25 | 2022-05-06 | 2022-05-13 | 2022-05-20 |  |  |  | 2022-06-03 | 2022-06-10 | 2022-06-17
Actual
4 | Motor Vehicle Repairs & Maintenance: Procurement of Tyres; Car accessories; and repair of Agency's vehicles | LASODA/G-F/NS/004/22 |  |  | 1543770 | <10M | NS | Post | Post | Plan | 2022-02-27 | NA | 2022-03-26 | 2022-05-07 | 2022-05-14 | 2022-05-21 |  |  |  | 2022-06-04 | 2022-06-11 | 2022-06-18
Actual
5 | Procurement of Stationery | LASODA/G-F/NS/005/22 |  |  | 698282 | <10M | NS | Post | Post | Plan | 2022-02-28 | NA | 2022-03-27 | 2022-05-08 | 2022-05-15 | 2022-05-22 |  |  |  | 2022-06-05 | 2022-06-12 | 2022-06-19
Actual
6 | MIS: Procurement of Toners, printers accessories, computer accessories, etc & their maintenance | LASODA/G-F/NS/006/22 |  |  | 1000000 | <10M | NS | Post | Post | Plan | 2022-03-02 | NA | 2022-03-30 | 2022-05-11 | 2022-05-18 | 2022-05-25 |  |  |  | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
7 | Procurement of Uniform Outfit for Driver and branded staff Uniform | LASODA/G/NS/007/22 |  |  | 350000 | <10M | NS | Post | Post | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
8 | PR&S UNIT EXPENSES: Annual Budget Preparation & procurement of Toners, A4 Papers Flash Drives, Large Envelopes, etc. | LASODA/G/NS/008/22 |  |  | 900000 | <10M | NS | Post | Post | Plan | 2022-02-28 | NA | 2022-03-27 | 2022-05-08 | 2022-05-15 | 2022-05-22 |  |  |  | 2022-06-05 | 2022-06-12 | 2022-06-19
Actual
9 | INTERNAL AUDIT: Procurement of Quarterly Auditing of Staff Materials & other Unit materials | LASODA/G/NS/009/22 |  |  | 600000 | <10M | NS | Post | Post | Plan | 2022-03-02 | NA | 2022-03-30 | 2022-05-11 | 2022-05-18 | 2022-05-25 |  |  |  | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
10 | PROCUREMENT UNIT: Procurement of Unit materials | LASODA/G/NS/010/22 |  |  | 500000 | <10M | NS | Post | Post | Plan | 2022-03-03 | NA | 2022-03-31 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  |  |  | 2022-06-09 | 2022-06-16 | 2022-06-23
Actual
11 | LEGAL SERVICES UNIT: Procurement of Legalpaedia, Legal Pavillion & conversion of Annual Journal to Braille version. | LASODA/G/NS/011/22 |  |  | 662000 | <10M | NS | Post | Post | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
12 | ICT UNIT EXPENSES: Procurement of Toners, A4 Papers Flash Drives, Large Envelopes, etc. | LASODA/G/NS/012/22 |  |  | 500000 | <10M | NS | Post | Post | Plan | 2022-02-28 | NA | 2022-03-27 | 2022-05-08 | 2022-05-15 | 2022-05-22 |  |  |  | 2022-06-05 | 2022-06-12 | 2022-06-19
Actual
13 | MRM&A DEPT: Procurement of medical accessories and other various consumables for the Department. | LASODA/G/NS/013/22 |  |  | 500000 | <10M | NS | Post | Post | Plan | 2022-03-02 | NA | 2022-03-30 | 2022-05-11 | 2022-05-18 | 2022-05-25 |  |  |  | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
14 | PUBLIC AFFAIRS UNIT: | LASODA/G/NS/014/22 |  |  | 250000 | <10M | NS | Post | Post | Plan | 2022-03-03 | NA | 2022-03-31 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  |  |  | 2022-06-09 | 2022-06-16 | 2022-06-23
Actual
15 | SOCIAL DEVELOPMENT & INTEGRATION: Provision of fund for Departmental working tools | LASODA/G/NS/015/22 |  |  | 500000 | <10M | NS | Post | Post | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
16 | BANKING OPERATION SYSTEM: Purchase of Counting Machines; Cash Bags; Till Boxes; and other Banking Activities for F&A Dept. | LASODA/G/NS/016/22 |  |  | 500000 | <10M | NS | Post | Post | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
17 | UNIFORM & PROTECTIVE OUTFIT: Provision of fund to Procure Uniforms for Staff & Driver | LASODA/G/NS/017/22 |  |  | 350000 | <10M | NS |  | Post | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
18 | VOCATIONAL SKILL: Training of PWDs on various vocational skills & Procurement of Training tools, materials & equipments. | LASODA/G/NS/018/22 |  |  | 38000000 | <50M | NS | PRE | Prior | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
19 | DIESEL: Purchase of Diesel for the Office Generator Plant - 70litres*10 working days*12 months | LASODA/G/NS/019/22 |  |  | 3360000 | <10M | NS | Post | Post | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
20 | EMPOWERMENT/ ENTREPRENEURSHIP FOR PWDs: Procurement of Peculiarity needs/ assistive on Inclusive/ special school study; Resource Centre for PWDs - Procurement of Infrastructure capacity (Leader factory, ICT Centre for CBT Exams for Blinds, etc. | LASODA/G/NCB/001/22 |  |  | 145097600 | <250M | NCB | PRE | Prior | Plan | 2022-03-04 | 2022-04-10 | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
21 | OFFICE FURNITURE & EQUIPMENT: Purchase of Office furniture & Equipment into the constructed Portal Cabin Office | LASODA/G/NS/020/22 |  |  | 18000000 | <50M | NS | Post | Prior | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual
22 | Procurement of 2nos Gubabi 4feet Office Safe D5 170 (Fire proof) | LASODA/G/NS/021/22 |  |  | 1200000 | <10M | NS | Post | Post | Plan | 2022-03-04 | NA | 2022-04-01 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  |  |  | 2022-06-10 | 2022-06-17 | 2022-06-24
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LASODA
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | RENOVATION OF LASODA OFFICE: (RETENTION) | LASODA/W/NS/001/22 |  | 2142140 | <10M | NS | Bill of Quantity | Post | Plan | Post | 2020-02-24 | 2020-03-16 | 2020-03-23 | 2020-05-04 | 2020-05-11 | 2020-05-18 |  |  | 42842803.89 | 2020-06-01 | 2020-06-08 | 2020-06-15 |  | 2022-03-14
[9 empty] | Actual |  | 2020-02-24 | 2020-07-17 | 2020-07-23 | 2020-07-30 |  |  | 2020-07-06 |  |  | 2020-08-11 | 2020-09-18 | 2020-11-10 | 2021-09-14
2 | RENOVATION & REHABILITATION OF LASODA AREA OFFICE @ 5 DIVISIONS (PHASE1) | LASODA/W/NS/002/22 | 3 | 30000000 | <50M | NS | Bill of Quantity | Prior | Plan | Prior | 2022-02-24 | 2022-03-16 | 2022-03-23 | 2022-05-04 | 2022-05-11 | 2022-05-18 |  |  |  | 2022-06-01 | 2022-06-08 | 2022-06-15
[9 empty] | Actual | [7 empty] | 2022-07-06
3 | PORTAL CABIN OFFICE: Construction of 40fts*25fts Portal Cabin Office for 2 Depts. & 3 Units with an in-built toilet. | LASODA/W/NS/003/22 |  | 24000000 | <50M | NS | Bill of Quantity | Prior | Plan | Prior | 2022-02-24 | 2022-03-16 | 2022-03-23 | 2022-05-04 | 2022-05-11 | 2022-05-18 |  |  |  | 2022-06-01 | 2022-06-08 | 2022-06-15
[9 empty] | Actual | [7 empty] | 2022-07-06